## Matrix_V11.6
Version 2016
DoD Manufacturing Readiness Levels (MRLs)
Acquisition Phase |  | Pre-Materiel Development Decision (Pre-MDD) |  |  | Materiel Solution Analysis (MSA) | Technology Maturation and Risk Reduction (TMRR) |  | Engineering & Manufacturing Development (EMD) |  | Low-Rate Initial Production (LRIP) | Full-Rate Production (FRP)
Technical Reviews |  |  |  |  | ASR | SRR/SFR | PDR | CDR | PRR/SVR | PCA
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
| Technology Maturity | Should be assessed at TRL 1. | Should be assessed at TRL 2. | Should be assessed at TRL 3. | Should be assessed at TRL 4. | Should be assessed at TRL 5. | Should be assessed at TRL 6. | Should be assessed at TRL 7 | Should be assessed at TRL 7 or TRL 8. | Should be assessed at TRL 8 or TRL 9. | Should be assessed at TRL 9.
A- Technology and Industrial Base | A.1 Industrial Base |  |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes. | Industrial base capabilities assessment initiated to identify potential manufacturing sources. Sole/single/ foreign source vendors and vendors of technologies with potential obsolescence issues have been identified and planning has begun to minimize risks. | Industrial base capabilities assessment for MS B has been completed. Industrial capability in place to support manufacturing of development articles. Plans to minimize sole/ foreign sources and obsolescence issues complete. Need for sole/single/foreign sources justified. Potential alternative sources identified. | Industrial capability to support production has been analyzed. Sole/single/foreign sources stability and obsolescence issues are assessed/monitored. Developing potential alternate sources as necessary. | Industrial base capability assessment for MS C has been completed. Industrial capability is in place to support LRIP. Sources are available, multi-sourcing where cost-effective or necessary to mitigate risk. | Industrial capability assessment for FRP has been completed and capability is in place to support start of FRP. | Industrial capability supports FRP and is assessed to support modifications, upgrades, surge and other potential manufacturing requirements.
| A.2 Manufacturing Technology Development |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified. | Required manufacturing technology development efforts initiated, if applicable. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production relevant environment. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production representative environment. | Primary manufacturing technology efforts concluding, and some improvement efforts continuing. Required manufacturing technology solutions validated on a pilot line. | Manufacturing technology process improvements efforts initiated for FRP. | Manufacturing technology continuous process improvements ongoing.
B - Design | B.1 Producibility Program |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies. | Producibility and manufacturability assessments of key technologies and components initiated as appropriate. Ongoing design trades consider manufacturing processes and industrial base capability constraints. Manufacturing processes assessed for capability to test and verify in production, and influence on Operations & Support. | Producibility assessments and producibility trade studies (performance vs. producibility) of key technologies/components completed. Results used to shape Acquisition Strategy, Systems Engineering Plan (SEP), Manufacturing and Producibility plans, and planning for EMD or technology insertion programs. Preliminary design choices assessed against manufacturing processes and industrial base capability constraints. Producibility enhancement efforts (e.g. Design For Manufacturing, Assembly, etc.) initiated. | Detailed producibility trade studies using knowledge of key design characteristics and related manufacturing process capability completed. Producibility enhancement efforts (e.g. Design for Manufacturability and Assembly) ongoing for optimized integrated system. Manufacturing processes re-assessed as needed for capability to test and verify potential influence on Operations & Support. | Producibility improvements implemented on system. Known producibility issues have been resolved and pose no significant risk for LRIP. | Prior producibility improvements analyzed for effectiveness during LRIP. Producibility issues/risks discovered in LRIP have been mitigated and pose no significant risk for FRP. | Design producibility improvements demonstrated in FRP. Process producibility improvements ongoing. All modifications, upgrades, Diminishing Manufacturing Sources & Material Shortages (DMSMS) and other changes assessed for producibility.
| B.2 Design Maturity | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts. | Lower level performance requirements sufficient to proceed to preliminary design. All enabling/critical technologies and components identified and the product lifecycle considered. Evaluation of design Key Characteristics (KC) initiated. Product data required for prototype component manufacturing released. | System allocated baseline established. Product requirements and features are well enough defined to support preliminary design review. Product data essential for subsystem/system prototyping has been released, and all enabling/critical component have been prototyped. Preliminary design KCs have been identified and mitigation plans in development. | Product design and features are well enough defined to support critical design review, even though design change traffic may be significant. All product data essential for component manufacturing has been released. Potential KC risk issues have been identified and mitigation plan is in place. | Detailed design of product features and interfaces is complete. All product data essential for system manufacturing has been released. Design change traffic does not significantly impact LRIP. Key Characteristics are attainable based upon pilot line demonstrations. | Major product design features and configuration are stable. System design has been validated through operational testing of LRIP items. Physical Configuration Audit (PCA) or equivalent complete as necessary. Design change traffic is limited. All KCs are controlled in LRIP to appropriate quality levels. | Product design is stable. Design changes are few and generally limited to those required for continuous improvement or in reaction to obsolescence. All KCs are controlled in FRP to appropriate quality levels.
C - Cost & Funding | C.1 Production Cost Knowledge (Cost modeling) |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified. | Prototype components produced in a production relevant environment, or simulations drive end-to-end cost models. Cost model includes materials, labor, equipment, tooling/Special Test Equipment (STE), setup, yield/scrap/rework, Work In Progress (WIP), and capability/capacity constraints. | Cost model updated with design requirements, material specifications, tolerances, integrated master schedule, results of system/subsystem simulations and production relevant prototype demonstrations. | Cost model updated with the results of systems/sub-systems produced in a production representative environment, production plant layout and design, and obsolescence solutions. | Cost models updated with results of pilot line build. | FRP cost model updated with result of LRIP build. | Cost model validated against actual FRP cost.
| C.2 Cost Analysis | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR). | Costs analyzed using prototype component actuals to ensure target costs are achievable. Decisions regarding design choices, make/buy, capacity, process capability, sources, quality, key characteristics, yield/rate, and variability influenced by cost models. | Costs analyzed using prototype system/sub-system actuals to ensure target costs are achievable. Allocate cost targets to subsystems. Cost reduction and avoidance strategies developed. Provide manufacturing cost drivers for "Should-Cost" models. | Manufacturing costs rolled up to system/sub-system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction and avoidance strategies underway. Update manufacturing cost drivers for "Should-Cost" models. | Costs analyzed using pilot line actuals to ensure target costs are achievable. Manufacturing cost analysis supports proposed changes to requirements or configuration. Cost reduction initiatives ongoing. Update manufacturing cost drivers for "Should-Cost" models. | LRIP cost goals met and learning curve analyzed with actual data. Cost reduction initiatives ongoing. Touch labor efficiency analyzed to meet production rates and elements of inefficiency are identified with plans in place for reduction. | FRP cost goals met. Cost reduction initiatives ongoing.
| C.3 Manufacturing Investment Budget | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 6 by MS B. All outstanding MRL 5 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 8 by MS C. Estimate includes capital investment for production-representative equipment by CDR and pilot line equipment by MS C. All outstanding MRL 6 risk areas understood with approved mitigation plans in place. | Program has updated budget estimate for reaching MRL 8 by MS C. All outstanding MRL 7 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for LRIP and FRP. All outstanding MRL 8 risk areas understood with approved mitigation plans in place. | Program has reasonable budget estimate for FRP. All outstanding MRL 9 risk areas understood with approved mitigation plans in place. | Production budgets sufficient for production at required rates and schedule to support funded program.
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.1 Maturity | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment. | Materials have been manufactured or produced in a prototype environment (may be in a similar application/program). Maturation efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place and material properties have been adequately characterized. | Material maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated during EMD as adequate to support LRIP. Material specification stable. | Material is controlled to specification in LRIP. Materials proven and validated as adequate to support FRP. | Material is controlled to specification in FRP.
| D.2 Availability |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated. | Availability issues addressed for prototype build. Significant material risks identified for all materials. Planning has begun to address scale-up issues. | Availability issues addressed to meet EMD build. Long-lead items identified. Components assessed for future DMSMS risk. | Availability issues addressed to meet LRIP builds. Long lead procurement identified and mitigated. DMSMS mitigation strategies for components in place. | Availability issues pose no significant risk for LRIP. Long lead procurement initiated for LRIP. Availability issues addressed to meet FRP builds. | Long lead procurement initiated for FRP. Availability issues pose no significant risk for FRP. | Program is in FRP with no significant material availability issues.
| D.3 Supply Chain Management |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources. | Potential supply chain sources identified and evaluated as able to support prototype build. | Lifecycle Supply Chain requirements updated. Critical suppliers list updated. Supply chain plans in place (e.g. teaming agreements, etc.) supporting an EMD contract award. | Effective supply chain management processes defined, documented, and in place. Plan developed for predictive indicators. Assessment of critical first tier supply chain completed (e.g. capability, capacity, etc.). | Assessment of critical second and lower tier supply chain completed. Robust requirements flow down processes in place and verified. Validated supplier compliance with program requirements and changes. Plan for predictive indicators updated and to be used in production. Supply chain adequate to support LRIP. | Long term agreements in place where practical. Prime's supplier management metrics (including thresholds and goals) in place and used to manage risks. Predictive indicators to manage suppliers in place. Supply chain is stable and adequate to support FRP. | Supply chain proven and supports FRP requirements.
| D.4 Special Handling (i.e. Government Furnished Property (GFP), shelf life, security, hazardous materials, storage environment, etc.) |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified. | Special handling procedures applied in production relevant environment. Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. | Special handling procedures applied in production relevant environment. Plans to address special handling requirement gaps complete. | Special handling procedures applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. | Special handling procedures applied in pilot line environment. Special handling procedures demonstrated in EMD or Technology Insertion Programs. Special handling issues pose no significant risk for LRIP. All work instructions contain special handling provisions as required. | Special handling procedures applied in LRIP environment. Special handling procedures demonstrated in LRIP. Special handling issues pose no significant risk for FRP. | Special handling procedures effectively implemented in FRP.
E - -Process Capability & Control | E.1 Modeling & Simulation (Product & Process) |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified. | Initial models/simulation (product or process) developed at the component level and used to determine constraints. | Initial models/simulation developed at the sub-system or system level, and used to determine system constraints. | Models/simulation used to determine system constraints and identify improvement opportunities. | Models/simulation verified by pilot line build. Results used to improve process and determine that LRIP requirements can be met. | Models/simulation verified by LRIP build, assists in management of LRIP, and determines that FRP requirements can be met. | Models/simulation verified by FRP build. Production simulation models used as a tool to assist in management of FRP.
| E.2 Manufacturing Process Maturity |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes. | Maturity has been assessed on similar processes in production. Process capability requirements have been identified for pilot line, LRIP and FRP. | Manufacturing processes demonstrated in production relevant environment. Begin collecting or estimating process capability data from prototype build and refine process capability requirements. | Manufacturing processes demonstrated in a production representative environment. Continue collecting or estimating process capability data and refine process capability requirements. | Manufacturing processes verified for LRIP on a pilot line. Process Capability data from pilot line meets target. Refine process capability requirements for LRIP and FRP based upon Pilot line data. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program LRIP objectives. Variability experiments conducted to show FRP impact and potential for continuous improvement. | Manufacturing processes are stable, adequately controlled, capable, and have achieved program FRP objectives.
| E.3 Process Yields and Rates |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA). | Target yields and rates established for pilot line, LRIP, and FRP. Yield and rate issues identified. Improvement plans developed/initiated. | Yields and rates from production relevant environment evaluated against targets and the results feed improvement plan. | Yields and rates from production representative environment evaluated against pilot line targets and the results feed improvement plans. | Pilot line targets achieved. Yields and rates required to begin LRIP refined using pilot line results. Improvement plans ongoing and updated. | LRIP yield and rate targets achieved. Yields and rates required to begin FRP refined using LRIP results. Yield improvements on-going. | FRP yield and rate targets achieved. Yield improvements on-going.
F - Quality Management | F.1 Quality Management |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP). | Quality strategy updated to reflect Key Characteristic identification activities. | Initial quality plan and quality management system is in place. Quality risks and metrics have been identified and improvement plans initiated. | Quality targets established. Quality Management System (QMS) elements (e.g., control of nonconforming material, corrective action, etc.) meet requirements of appropriate industry standards. Program-specific Quality Program Plan being developed. | Program-specific Quality Program Plan and Quality Manager established. Quality targets assessed against pilot line, results feed continuous quality improvements. | Quality targets verified on LRIP line. Continuous quality improvement on-going. Management review of Quality measures is conducted on regular basis and appropriate action is taken. | Quality targets verified on FRP line. Continuous quality improvement on-going. Statistical controls applied where appropriate.
| F.2 Product Quality |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP). | Roles and responsibilities identified for acceptance test procedures, in-process and final inspections, and statistical process controls for prototype units. | Key Characteristic management approach defined. Initial requirements identified for acceptance test procedures and in-process and final inspection requirements for EMD units. Appropriate inspection and acceptance test procedures identified for prototype units. | Quality data from the production representative environment collected and analyzed and results used to shape improvement plans. Control plans completed for management of Key Characteristics. Test and Inspection plans being developed for EMD units. | Key Characteristics managed. Measurement procedures and controls in place (e.g. SPC, FRACAS, audits, customer satisfaction, etc.). Pilot line data meets capability requirements for all Key Characteristics. Test and Inspection plans complete and validated for production units. | Data from LRIP demonstrates production processes for all Key Characteristics and other manufacturing processes critical to quality are capable and under control for FRP. | Quality of Key Characteristics controlled at rate, data reflects only rare and unrepeated quality issues related to manufacturing processes. Results achieve targeted statistical level on all Key Characteristics. Results reflect continuous improvement.
| F.3 Supplier Quality Management |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management. | Supply base quality capabilities and risks identified, including subtier supplier quality management. | Supply base quality improvement initiatives identified addressing supplier Quality Management System shortfalls, including subtier supplier quality management. | Key supplier Quality Managemetn Systems meet appropriate industry standards. Supplier quality data from production representative units collected and analyzed. Strategy for audits of critical supplier processes outlined. | Supplier program-specific Quality Management Systems are adequate. Supplier products have completed qualification testing and first article inspection. Acceptance testing of supplier products is adequate to begin LRIP. Plan for subcontractor process audits in place and implemented by prime contractor. | Supplier management of quality of Key Characteristics and other critical manufacturing processes demonstrates capability and control for FRP. Acceptance testing of supplier products reflects control of quality adequate to begin FRP. Subcontractor Quality Audits performed as necessary to ensure subcontractor specification compliance. | Supplier quality data reflects adequate management of Key Characteristics and control of critical manufacturing processes, including quality management down to subtier suppliers. Results achieve high statistical level (e.g. 6-sigma) on all critical dimensions. Subcontractor Quality Audits performed as necessary to ensure subcontractor specification compliance.
G - Manufacturing Workforce (Engineering & Production) | G.1 Manufacturing Workforce (Engineering & Production) |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase. | Skill sets identified and plans developed to meet prototype and production needs. Special skills certification and training requirements established. | Manufacturing workforce skills available for production in a relevant environment. Identify resources (quantities and skill sets) and develop initial plans to achieve requirements for pilot line and production. | Manufacturing workforce resource requirements identified for pilot line. Plans developed to achieve pilot line requirements. Plans updated to achieve LRIP workforce requirements. Pilot line workforce trained in production representative environment. | Manufacturing workforce resource requirements identified for LRIP. Plans developed to achieve LRIP requirements. Plans updated to achieve FRP workforce requirements. LRIP personnel trained on pilot line where possible. | LRIP personnel requirements met. Implement plan to achieve FRP workforce requirements. | FRP personnel requirements met. Production workforce skill sets maintained due to attrition of workforce.
H - Facilities | H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA. | Identify tooling and STE/SIE requirements and provide supporting rationale and schedule. | Prototype tooling and STE/SIE concepts demonstrated in production relevant environment. Production tooling and STE/SIE requirements developed. | Production tooling and STE/SIE design and development efforts underway and validation plans for STE/SIE are complete. Manufacturing equipment maintenance strategy developed. | Tooling, test and inspection equipment proven on pilot line and additional requirements identified for LRIP. STE/SIE validated as part of pilot line validation IAW validation plan. Manufacturing equipment maintenance demonstrated on pilot line. | All tooling, test and inspection equipment proven in LRIP and additional requirements identified for FRP. Manufacturing equipment maintenance schedule demonstrated. STE/SIE validation maintained as necessary. Revalidation completed as necessary. | Proven tooling, test and inspection equipment in place to support maximum FRP. Planned equipment maintenance schedule achieved. STE/SIE validation maintained as necessary. Revalidation completed as necessary.
| H.2 Facilities |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA. | Manufacturing facilities identified and plans developed to produce prototypes. | Manufacturing facilities identified and plans developed to produce pilot line build. | Manufacturing facilities identified and plans developed to produce LRIP build. | Pilot line facilities demonstrated. Manufacturing facilities adequate to begin LRIP. Plans in place to support transition to FRP. Workplace safety is adequate. | Manufacturing facilities in place and demonstrated in LRIP. Capacity plans adequate to support FRP. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements.
I - Manufacturing Management | I.1 Manufacturing Planning & Scheduling |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy. | Manufacturing strategy refined based upon preferred concept. Prototype schedule risk mitigation efforts initiated. | Initial manufacturing approach developed. All system design related Manufacturing events included in Integrated Master Plan/Schedule (IMP/S). Manufacturing risk mitigation approach for pilot line or technology insertion programs defined. | Initial manufacturing plan developed. Manufacturing planning included in IMP/S. Manufacturing risks integrated into risk mitigation plans. Initial work instructions developed. Effective production control system in place to support pilot line. | Manufacturing plan updated for LRIP. All key manufacturing risks are identified and assessed with approved mitigation plans in place. Work instructions finalized. Effective production control system in place to support LRIP. | Manufacturing plan updated for FRP. All manufacturing risks tracked and mitigated. Effective production control system in place to support FRP. | All manufacturing risks mitigated.
| I.2 Materials Planning |  |  |  | Technology development article component list developed with associated lead time estimates. | Technology development part list maturing, Make/buy evaluations begin, and include production considerations reflecting Pilot line, LRIP, and FRP needs. Lead times and other risks identified. | Most material decisions complete (make/buy), material risks identified and mitigation plans developed. Bill of Materials (BOM) initiated. | Make/Buy decisions and BOM complete for pilot line build. Material planning systems in place for pilot line build. | Make/Buy decisions and BOM complete to support LRIP. Material planning systems proven on pilot line for LRIP build. | Make/Buy decisions and BOM complete to support FRP. Material planning systems proven in LRIP and sufficient for FRP. | Material planning systems validated on FRP build.
A
FRP
C
B
MDD

## MRL Thread Focus
Thread | Sub-Thread
A - Technology and Industrial Base | A.1: Industrial Base
A.2: Manufacturing Technology Development
B - Design | B.1: Producibility Program
B.2: Design Maturity
C - Cost & Funding | C.1: Production Cost Knowledge (Cost modeling)
C.2: Cost Analysis
C.3: Manufacturing Investment Budget
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.1: Material Maturity
D.2: Material Availability
D.3: Supply Chain Management
D.4: Special Handling
E - Process Capability & Control | E.1: Modeling & Simulation (Product & Process)
E.2: Manufacturing Process Maturity
E.3: Process Yields and Rates
F - Quality Management | F.1: Quality Management
F.2: Product Quality
F.3: Supplier Quality Management
G - Manufacturing Workforce (Engineering & Production) | G.1: Manufacturing Workforce (Engineering & Production)
H - Facilities | H.1: Tooling, Special Test and Inspection Equipment (STE/SIE)
H.2 : Facilities
I - Manufacturing Management | I.1: Manufacturing Planning & Scheduling
I.2: Materials Planning

## MRL 1-4 Sub-Thread Focus
Sub-Thread | Thread Artifact Outcome | MRL 1-3 Activity Focus | MRL 1-3 Knowledge Development Focus
B.1: Producibility Program | Producibility & Manufacturability Optimization | Analyzing/Understanding (Assessing/Evaluating) | Producibility Trade Study Model Development (Analogous to Reliability Prediction)
C.1: Production Cost Knowledge (Cost modeling) | Cost Model Development & Refinement | Analyzing/Understanding (Assessing/Evaluating) | Technology Cost-Benefit Analysis & Value Proposition Development
D.1: Material Maturity | Material Specification Development | Analyzing/Understanding (Assessing/Evaluating) | Processing-Structure-Property Relationships (Critical Raw Materials & Components)
E.2: Manufacturing Process Maturity | Manufacturing Process Capability Management | Analyzing/Understanding (Assessing/Evaluating) | Process Stability and Repeatability Relationships (Critical Manufacturing Processes)
A.1: Industrial Base | Industrial Base Capability Assessments | Assessing/Evaluating | Global Industrial Base Landscape Evaluation (Make & Buy Production System Elements)
B.2: Design Maturity | Product Specification Development | Assessing/Evaluating | Technology Insertion MOE Linkages (Precursor to System KPP Development)
C.2: Cost Analysis | Design to Cost Methodology & Cost Feasibility | Assessing/Evaluating | System Affordability & LCC Reduction Needs Development
D.3: Supply Chain Management | Manufacturing "Buy" Strategy | Assessing/Evaluating | Supply Chain Capability & Capacity Needs (Buy Production System Elements)
E.1: Modeling & Simulation (Product & Process) | Model-Based Product & Process Optimization | Assessing/Evaluating | Model Based Systems Engineering Needs
E.3: Process Yields and Rates | Manufacturing Yield & Throughput Management | Assessing/Evaluating | Capacity Utilization & Yield Estimates (Make & Buy Production System Elements)
F.1: Quality Management | Quality Management System Development | Assessing/Evaluating | Quality Management System Development Needs (Non-Materiel Solutions)
F.3: Supplier Quality Management | Sub-Tier Supplier Flow Down Specifications | Assessing/Evaluating | Supplier Quality Management Needs (Buy Production System Elements)
G.1: Manufacturing Workforce (Engineering & Production) | K-Gray Workforce Development & Training | Assessing/Evaluating | Next-Gen Workforce Development Skill Set Needs (Includes STEM Program Alignment)
H.2 : Facilities | Manufacturing "Make" Strategy | Assessing/Evaluating | Manufacturing Facility Development Needs (Make Production System Elements)
A.2: Manufacturing Technology Development | Manufacturing Technology Transition Plan | Planning/Executing (Strategic) | Manufacturing Technology Roadmap Development & Refinement (Materiel Solutions)
C.3: Manufacturing Investment Budget | Manufacturing Budget Program Management | Planning/Executing (Strategic) | Manufacturing Technology Investment Portfolio Management (Materiel Solutions)
D.2: Material Availability | Critical Material Procurement & Obsolescence Management | Planning/Executing (Strategic) | Proactive Critical Material, Obsolescence, & DMSMS Risk Management Forecasting
I.1: Manufacturing Planning & Scheduling | Manufacturing Strategy/Plan Development | Planning/Executing (Strategic) | Manufacturing Competitiveness Strategy (Materiel & Non-Materiel Solutions)
I.2: Materials Planning | Make/Buy Decisions & BOM Development | Planning/Executing (Strategic/Tactical) | Integration of Manufacturing Planning into Early Development Planning and S&T Activities
D.4: Special Handling | Special Handling Procedure Development | Planning/Executing (Tactical) | Technology Raw Material & Component Special Handling Considerations (Materiel Solutions)
F.2: Product Quality | Inspection & Acceptance Test Methods/Criteria | Planning/Executing (Tactical) | Technology Validation & Verification Methods/Criteria (Materiel Solutions)
H.1: Tooling, Special Test and Inspection Equipment (STE/SIE) | Special Tooling, Test, & Inspection Equipment | Planning/Executing (Tactical) | Technology Tooling/STE/SIE Considerations (Prototype Specimens, Devices, Components)

## MRL 1-4 Draft Criteria
Sub-Thread | Thread Artifact Outcome | MRL 1-3 Activity Focus | MRL 1-3 Knowledge Development Focus | MRL 1 | MRL 2 | MRL 3 | MRL 4
B.1: Producibility Program | Producibility & Manufacturability Optimization | Analyzing/Understanding (Assessing/Evaluating) | Producibility Trade Study Model Development (Analogous to Reliability Prediction) | Descriptive studies performed to generate hypotheses about qualitative cause-effect relationships between critical technology variables and design dependent producibilty and manufacturability parameters. Design applications limited to material and/or process families/classes associated with the implementation of the technology. | Analytic studies performed to test and validate hypotheses about cause-effect relationships and establish quantitative correlations between critical technology variables and design dependent producibility and manufacturability parameters. Design applications limited to generic device families associated with the implementation of the technology, with potential part families for technology insertion identified which may be speculative. | Analytical and laboratory studies performed to develop and validate predictive models to quantify cause-effect relationships between critical technology variables and design dependent producibility and manufacturability parameters. Design applications identified that consist of distinctive part families associated with demonstrating practical applications of the technology. | Initial producibility and manufacturability assessment of preferred systems concepts completed and results incorporated into AoA trade studies. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
C.1: Production Cost Knowledge (Cost modeling) | Cost Model Development & Refinement | Analyzing/Understanding (Assessing/Evaluating) | Technology Cost-Benefit Analysis & Value Proposition Development | Descriptive studies performed to generate hypotheses about qualitative cost-benefit estimates associated with how the technology impacts system-level affordability. Value propositions formulated in terms of relative benefits associated with applications of the technology that are limited to material and/or process families/classes. | Analytic studies performed to validate rough order of magnitude (ROM) cost-benefit estimates associated with implementing the technology into practical applications. Value propositions formulated in terms of generic device application families associated with implementation of the technology, with potential part families identified for technology transition as part of the value proposition which may be speculative. | Analytical models developed and validated to predict and quantify ROM cost-benefit estimates associated with implementing the technology into distinctive types of part families associated with production hardware. Value propositions formulated in terms of potential technology transition opportunities that identify specific product families that utilize the types of part families upon which the cost-benefit analyses are based. | Potential product classes/lines identified that are associated with the types of technology insertion applications upon which the cost-benefit analyses are based. Cost-benefit estimates refined based on the actual production volumes associated with the system concepts considered in the AoA. Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
D.1: Material Maturity | Material Specification Development | Analyzing/Understanding (Assessing/Evaluating) | Processing-Structure-Property Relationships (Critical Raw Materials & Components) | Descriptive studies performed to generate hypotheses about qualitative processing-structure-property relationships for new material and component technology development efforts. | Analytic studies performed to test and validate hypotheses about processing-structure-property relationships and establish quantitative correlations that describe these relationships for new material and component technology development efforts. | Analytical and laboratory studies performed to develop and validate predictive models to quantify processing-structure-property relationships for new material and component technologies. | Projected materials and components have been produced in a laboratory environment with processing-structure-property relationships demonstrated to be controllable and repeatable.
E.2: Manufacturing Process Maturity | Manufacturing Process Capability Management | Analyzing/Understanding (Assessing/Evaluating) | Process Stability and Repeatability Relationships (Critical Manufacturing Processes) | Descriptive studies performed to generate hypotheses about qualitative cause-effect relationships between critical process control variables and process stability and repeatability for critical manufacturing processes. | Analytic studies performed to test and validate hypotheses about cause-effect relationships and establish quantitative correlations between critical process control variables and process stability and repeatability for critical manufacturing processes. | Analytic and laboratory studies performed to develop and validate predictive models that quantify cause-effect relationships between critical process control variables and process stability and repeatability for critical manufacturing processes. | Complete a survey to determine the current state of critical processes for preferred system concepts and supply chain sources. Process capability technical requirements and improvement plans developed and incorporated into the SEP for critical processes and supply chain sources.
A.1: Industrial Base | Industrial Base Capability Assessments | Assessing/Evaluating | Global Industrial Base Landscape Evaluation (Make & Buy Production System Elements) | Current state global industrial base capabilities in key manufacturing functional areas identified along with global trends in emerging manufacturing capabilities. Future state industrial base manufacturing landscape shift scenarios in key manufacturing functional areas developed and incorporated into the manufacturing CONOPS analysis. | Industrial base manufacturing capability, competency, and competitiveness gaps in key manufacturing functional areas identified and prioritized in terms of operational risk. Future state industrial base footprint strategy defined and linked to the industrial base landscape shift scenarios associated with the manufacturing CONOPS analysis. | Industrial base manufacturing capability, competency, and competitiveness benchmarks for potential sources within the footprint assessed and characterized. Future state industrial base operational requirements defined that include measures of effectiveness (MOE's) with minimum and desired levels established that quantify when the desired industrial base sources have been sufficiently developed. | Industrial base capabilities of preferred sources within the footprint surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes and used to develop industrial base technical requirements. Plans to develop preferred sources and address known gaps/risks established that are linked to the industrial base development MOE's.
B.2: Design Maturity | Product Specification Development | Assessing/Evaluating | Technology Insertion MOE Linkages (Precursor to System KPP Development) | Potential design applications identified that are limited to material and/or process families/classes associated with the implementation of the technology to address known system capability shortcomings. Manufacturing considerations incorporated into the system CONOPS need and gap analysis being considered in pre-MDD early development planning activities. | Potential design applications identified that are limited to generic device families associated with the implementation of the technology to address prioritized capability gaps, with potential part family applications for technology insertion identified which may be speculative. Potential design and manufacturing solution types identified that address prioritized operational capability gaps being considered in pre-MDD early development planning activities. | Potential design applications identified that consist of distinctive part families associated with demonstrating practical applications of the technology to address system and manufacturing CONOPS capability gaps. Product operational requirements developed that include measures of effectiveness (MOE's) to evaluate potential design and manufacturing solution approaches being considered in pre-MDD early development planning activities. | Potential design applications identified that are linked to distinctive product families associated with the system concepts and technical requirements being considered in the AoA trade studies. SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
C.2: Cost Analysis | Design to Cost Methodology & Cost Feasibility | Assessing/Evaluating | System Affordability & LCC Reduction Needs Development | Current state system affordability shortcomings associated with the baseline system CONOPS identified. Future state system affordability improvement areas identified and incorporated into the system CONOPS need and gap analysis being considered in pre-MDD early development planning activities. | System affordability gaps identified and prioritized in terms of life cycle cost (LCC) impact. Potential system affordability solution type recommendations developed that address prioritized LCC reduction areas being considered in pre-MDD early development planning activities. | System affordability gaps characterized with specific affordability solution recommendations provided along with key LCC impact assumptions, limitations, and boundary conditions. System affordability requirements/constraints developed and incorporated into the system measures of effectiveness (MOE's) to enable the integration and evaluation of LCC reduction opportunities into pre-MDD early development planning activities. | System affordability and producibility cost risks assessed during system trade studies. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR). Initial potential Key Performance Parameters (KPP's) associated with LCC cost reduction activities for the preferred system concept and incorporated into the SEP and/or manufacturing maturation plan (MMP).
D.3: Supply Chain Management | Manufacturing "Buy" Strategy | Assessing/Evaluating | Supply Chain Capability & Capacity Needs (Buy Production System Elements) | Current state supplier capability and capacity shortcomings for buy production system element supply chain sources on the Approved Supplier List (ASL) identified. Future state supplier capability and capacity development needs in key manufacturing functional areas established and incorporated into the manufacturing CONOPS. | Supply chain capability and capacity gaps associated with the current ASL and desired supply chain footprint identified and prioritized in terms of manufacturing CONOPS operational risk. Recommendations for broad types of alternative supply chain sources and supplier development solutions developed to address prioritized supply chain capability and capacity gaps for buy production system elements associated with the future state industrial base footprint strategy. | Supply chain capability and capacity gaps characterized for potential supply chain sources on the ASL that support the manufacturing CONOPS with recommendations for specific solutions to address the gaps provided along with supplier development assumptions, limitations, and boundary conditions. Industrial base operational requirements updated to incorporate source selection and supplier development requirements for buy production system elements associated with the desired industrial base footprint. | Survey completed for potential supply chain sources to determine their capability and capacity to support the manufacturing CONOPS and incorporated into the AoA. Source selection technical requirements developed and used to down-select preferred sources for buy production system elements associated with the preferred system concept. Supplier development technical requirements established to address documented supply chain capability gaps and incorporated into the manufacturing maturation plan (MMP).
E.1: Modeling & Simulation (Product & Process) | Model-Based Product & Process Optimization | Assessing/Evaluating | Model Based Systems Engineering Needs | Current state manufacturing modeling/simulation capability shortcomings identified based on the ability to support manufacturing model based systems engineering (MBSE) activities. Future state manufacturing MBSE capability development needs identified and used to shape a high-level manufacturing MBSE development strategy to address current state manufacturing modeling/simulation capability shortcomings. | Manufacturing modeling/simulation capability gaps identified and prioritized with recommendations provided to pursue types of MBSE solutions to address the gaps and provide the needed future state capabilities. Draft manufacturing modeling/simulation roadmap developed that provides a preliminary manufacturing MBSE development strategy to mature the various types of solutions being recommended. | Manufacturing modeling/simulation capability gaps characterized with specific MBSE solution approaches to address gaps identified and assessed to define key assumptions, limitations, and boundary conditions associated with the evaluations Manufacturing MBSE roadmap updated to document and define specific solution approaches to address the prioritized manufacturing modeling/simulation capability gaps. | Production system manufacturing modeling/simulation approaches for process or product are identified and incorporated into the system and manufacturing concept MBSE strategy.
E.3: Process Yields and Rates | Manufacturing Yield & Throughput Management | Assessing/Evaluating | Capacity Utilization & Yield Estimates (Make & Buy Production System Elements) | Current state manufacturing yield estimate baselines and capacity utilization rates defined for critical manufacturing processes and supply chain sources of critical materials and components in the ASL. Future state manufacturing yield and capacity utilization rate improvement areas for critical processes and suppliers identified and incorporated into the manufacturing CONOPS and supplier development plans. | Manufacturing yield and capacity utilization rate improvement targets for critical manufacturing processes and suppliers defined and prioritized based on operational risk to the manufacturing CONOPS. Broad types of solutions defined that provide a path forward to achieve the yield and capacity utilization rate targets in the manufacturing CONOPS for all critical manufacturing processes and suppliers identified in the ASL. | Manufacturing yield and capacity utilization rate gaps characterized for critical processes and suppliers with specific solutions to address gaps and mitigate the operational risk of achieving the targets identified and evaluated. Industrial base operational requirements for yield and capacity utilization rate improvements developed with industrial base measures of effectiveness updated to include yield and capacity utilization rate considerations for critical processes and supply chain sources. | Yield and rates assessment on proposed/similar processes complete for the alternative systems and manufacturing concepts and technical requirements for improvements developed and applied within Analysis of Alternatives (AoA). Manufacturing yield and capacity utilization rate improvement targets validated for the preferred system and manufacturing concept and incorporated in the manufacturing maturation plan (MMP).
F.1: Quality Management | Quality Management System Development | Assessing/Evaluating | Quality Management System Development Needs (Non-Materiel Solutions) | Current state quality management system capability shortcomings identified along with trends in emerging quality management system technological capabilities (e.g., information technology solutions, metrology solutions, data analytics solutions). Future state quality management system improvement areas associated with non-materiel solution investments identified and incorporated into the manufacturing competitiveness strategy. | Quality management system capability gaps prioritized in terms of manufacturing CONOPS operational risk. Recommendations for broad types of alternative quality management system technological non-materiel solutions developed to address prioritized quality management system gaps and incorporated into the manufacturing competitiveness strategy. | Quality management system capability gaps characterized with recommendations for specific quality management system technological non-materiel solutions to address the gaps provided and incorporated into the manufacturing competitiveness strategy. | Quality strategy identified for the preferred system concept as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP). Quality management system improvement plans updated to incorporate technological non-materiel solutions to address known capability gaps.
F.3: Supplier Quality Management | Sub-Tier Supplier Flow Down Specifications | Assessing/Evaluating | Supplier Quality Management Needs (Buy Production System Elements) | Current state supplier quality management shortcomings for buy production system element supply chain sources on the Approved Supplier List (ASL) identified. Future state supplier quality management development needs in key manufacturing functional areas established and incorporated into the manufacturing CONOPS. | Supply chain quality management gaps associated with the current ASL and desired supply chain footprint identified and prioritized in terms of manufacturing CONOPS operational risk. Recommendations for broad types of alternative supply chain sources and supplier development solutions developed to address prioritized supply chain quality management gaps for buy production system elements associated with the future state industrial base footprint strategy. | Supply chain quality management gaps characterized for potential supply chain sources on the ASL that support the manufacturing CONOPS with recommendations for specific solutions to address the gaps provided along with supplier development assumptions, limitations, and boundary conditions. Industrial base operational requirements updated to incorporate supplier quality management requirements for buy production system elements associated with the desired industrial base footprint. | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management. Supplier quality management technical requirements developed and used to down-select preferred sources for buy production system elements associated with the preferred system concept. Supplier development technical requirements established to address documented supply chain quality management gaps and incorporated into the manufacturing maturation plan (MMP).
G.1: Manufacturing Workforce (Engineering & Production) | K-Gray Workforce Development & Training | Assessing/Evaluating | Next-Gen Workforce Development Skill Set Needs (Includes STEM Program Alignment) | Specialized manufacturing workforce skill set needs in key engineering and manufacturing functional areas identified along with shortcomings in current STEM and workforce development programs to deliver the needed human capital capabilities. Manufacturing CONOPS updated to establish linkages with ongoing STEM programs and regional workforce development initiatives for critical engineering and manufacturing skill set needs. | Specialized manufacturing workforce skill set gaps identified and prioritized in terms of manufacturing CONOPS operational risk. Recommendations for new types of STEM and workforce development training solutions and/or enhancements to ongoing programs identified that have the potential to deliver new human capital capabilities to support the future state manufacturing CONOPS. | Specialized manufacturing workforce skill set gaps characterized with specific STEM and workforce development solution recommendations provided on ways to improve the effectiveness and efficiency of ongoing and new programs to deliver the needed human capital capabilities. Industrial base operational requirements updated to incorporate specialized engineering and manufacturing skill sets required to support the manufacturing CONOPS. | Manufacturing skill sets associated with the types of system and manufacturing concepts being evaluated in the AoA identified and manufacturing workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
H.2 : Facilities | Manufacturing "Make" Strategy | Assessing/Evaluating | Manufacturing Facility Development Needs (Make Production System Elements) | Specialized manufacturing and test facility capability and capacity needs and constraints for buy production system elements associated with the manufacturing CONOPS identified. Future state manufacturing and test facility capital investment areas to address capability and capacity need shortcomings evaluated and incorporated into the manufacturing CONOPS. | Specialized manufacturing and test facility capability and capacity gaps identified and prioritized based on manufacturing CONOPS operational risk. Recommendations for broad types of alternative facility and capital investment solutions developed for make production system elements to address prioritized facility capability and capacity gaps for make production system elements associated with the future state industrial base footprint strategy. | Specialized manufacturing and test facility capability and capacity gaps characterized with specific capital investment solutions identified to address the gaps along with return on investment estimates. Specialized facility capital investment operational requirements to support the industrial base footprint and manufacturing competitiveness strategies developed and incorporated into the manufacturing CONOPS. | Technical requirements for specialized facility capital equipment to address alternative system and manufacturing concepts developed and incorporated into the AoA. Availability of manufacturing facilities that meet capability and capacity technical requirements for prototype development and production evaluated as part of AoA.
A.2: Manufacturing Technology Development | Manufacturing Technology Transition Plan | Planning/Executing (Strategic) | Manufacturing Technology Roadmap Development & Refinement (Materiel Solutions) | Current state manufacturing capability shortcomings and advanced manufacturing technology capabilities identified that describe how the industrial base will perform enduring manufacturing functions 3-5 years in the future. Global manufacturing trends in emerging advanced manufacturing technologies identified and used to shape a high-level initial manufacturing technology development strategy to address current state industrial base capability shortcomings. | Manufacturing capability gaps identified and prioritized with recommendations provided to pursue types of advanced manufacturing solutions to address the gaps and provide the needed future state capabilities. Draft manufacturing technology roadmap developed that provides a preliminary manufacturing technology development strategy to mature the various types of solutions being recommended. | Manufacturing capability gaps characterized with specific solution approaches to address gaps identified and assessed to define key assumptions, limitations, and boundary conditions associated with the evaluations Manufacturing technology roadmap updated to document and define specific solution approaches to address the prioritized manufacturing capability gaps. | Initial determination of potential advanced manufacturing critical technology elements (CTE's) associated with roadmap gap closure solution approaches. Manufacturing Science & Advanced Manufacturing Technology requirements associated with each advanced manufacturing CTE identified, validated and incorporated into the advanced manufacturing technology roadmap.
C.3: Manufacturing Investment Budget | Manufacturing Budget Program Management | Planning/Executing (Strategic) | Manufacturing Technology Investment Portfolio Management (Materiel Solutions) | Manufacturing technology portfolio investment strategy developed from a multi-agency and/or multi-stakeholder perspective that leverages investment synergies to develop cross-cutting advanced manufacturing capabilities 3-5 years in the future that address current state industrial base manufacturing capability shortcomings. | Recommendations to pool resources and develop joint investment strategies to address cross-cutting advanced manufacturing technology solutions developed. Manufacturing technology roadmap updated top reflect multi-agency and/or multi-stakeholder investment priorities. | Annual operating plans developed that define advanced manufacturing technology investments required to support current year roadmap gap closure priorities with multi-agency and/or multi-stakeholder cost-benefit analyses documented that provide rationale for needed investments. Specific technology transition targets identified and validated for joint investment concepts. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.2: Material Availability | Critical Material Procurement & Obsolescence Management | Planning/Executing (Strategic) | Proactive Critical Material, Obsolescence, & DMSMS Risk Management Forecasting | Current state critical material, obsolescence, and DMSMS issues and risks identified along with forecasts for projected trends. Proactive approaches looking 3-5 years in the future defined that identify areas where manufacturing technology development efforts can be leveraged to address evolving gaps and risks. | Critical material, obsolescence, and DMSMS issues identified and prioritized in terms of operational risk. Manufacturing technology roadmaps updated to incorporate critical material, obsolescence, and DMSMS stakeholder needs into multi-agency investment strategies. | Alternative materials and manufacturing technology solutions to address material availability gaps identified and characterized. Key assumptions, limitations, and boundary conditions associated with potential solution approaches documented and used to develop risk mitigation plans. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated with material availability risks incorporated into AoA trade studies and risk mitigation plans incorporated into SEP for the preferred system concept.
I.1: Manufacturing Planning & Scheduling | Manufacturing Strategy/Plan Development | Planning/Executing (Strategic) | Manufacturing Competitiveness Strategy (Materiel & Non-Materiel Solutions) | Current state manufacturing competitiveness gaps identified along with forecasts for projected trends. Proactive approaches looking 3-5 years in the future defined that identify materiel (i.e., technology, capital, workforce) and non-materiel (i.e., quality, cost, location) solution investment areas and used to shape a high-level manufacturing competitiveness strategy. | Manufacturing competitiveness gaps identified and prioritized in terms of operational risk. Manufacturing competitiveness strategy refined with manufacturing technology roadmaps and investment budgets updated to incorporate materiel solution approaches and factory capital investment strategic plans updated to incorporate non-materiel solution approaches. | Manufacturing competitiveness gaps characterized with specific materiel and non-materiel solution recommendations developed and incorporated the manufacturing competitiveness strategy. Materiel solution recommendations incorporated into manufacturing technology roadmaps and non-materiel solution recommendations incorporated into factory capital planning. | Overall manufacturing strategy for the preferred system concept developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy. Factory capital investment budgets approved and have sufficient funding to implement non-materiel solutions into facility operations.
I.2: Materials Planning | Make/Buy Decisions & BOM Development | Planning/Executing (Strategic/Tactical) | Integration of Manufacturing Planning into Early Development Planning and S&T Activities | Current state system operational capability shortcomings analyzed and used to identify relevant standard program Work Breakdown Structure (WBS) templates (see MIL-STD-881C) associated with the relevant system types being considered and used to incorporate manufacturing planning into pre-MDD CONOPS needs validation processes, Program WBS templates used to help identify system-level technology insertion opportunities for basic science and technology (S&T) efforts associated with understanding physical phenomena. | Prioritized system operational capability gaps analyzed and used to identify relevant standard program Work Breakdown Structure (WBS) templates (see MIL-STD-881C) associated with the types of system solution concepts being recommended and used to incorporate manufacturing planning considerations into pre-MDD Capability Based Assessment (CBA) processes. Program WBS templates used to help identify potential system-level technology insertion opportunities for practical applications of science and technology (S&T) efforts which may be speculative. | Characterized system operational capability gaps analyzed and used to identify relevant standard program Work Breakdown Structure (WBS) templates (see MIL-STF-881C) associated with specific solution concepts being recommended and used to incorporate manufacturing planning considerations into pre-MDD activities that support Initial Capabilities Document (ICD) development processes. Program WBS templates used to help identify distinctive system-level technology insertion opportunities for the types of part family applications identified for practical applications of science and technology (S&T) development efforts. | Preliminary program Work Breakdown Structure (WBS) developed from templates (see MIL-STD-881C) that includes manufacturing planning considerations for preferred system concepts (e.g., systems engineering, system test and evaluation, training, data, industrial facilities, peculiar support equipment) development needs for preferred system concepts . Technology development article demonstration vehicle component parts list developed for all technology development efforts with associated procurement lead time estimates .
D.4: Special Handling | Special Handling Procedure Development | Planning/Executing (Tactical) | Technology Raw Material & Component Special Handling Considerations (Materiel Solutions) | Raw material and component special handling needs/requirements identified for material and/or process family/class specimen testing required to support hypothesis development to establish qualitative cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Raw material and component special handling needs/requirements identified for device family hardware testing required to support hypothesis validation to establish quantitative correlations between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Raw material and component special handling needs/requirements identified for part family component testing required to support analytical model development and validation for the quantitative prediction of cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | List of hazardous materials associated with the system concept refinement and/or technology development updated. Special handling procedures applied in the lab for prototype hardware fabrication. Special handling requirements identified for preferred system concepts and incorporated into the Systems Engineering Plan (SEP).
F.2: Product Quality | Inspection & Acceptance Test Methods/Criteria | Planning/Executing (Tactical) | Technology Validation & Verification Methods/Criteria (Materiel Solutions) | Validation and verification methods/criteria defined for material and/or process family/class specimen testing required to support hypothesis development to establish qualitative cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Validation and verification methods/criteria defined for device family hardware testing required to support hypothesis validation to establish quantitative correlations between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Validation and verification methods/criteria defined or part family component testing required to support analytical model development and validation for the quantitative prediction of cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Product inspection and acceptance testing strategy for preferred system concepts identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
H.1: Tooling, Special Test and Inspection Equipment (STE/SIE) | Special Tooling, Test, & Inspection Equipment | Planning/Executing (Tactical) | Technology Tooling/STE/SIE Considerations (Prototype Specimens, Devices, Components) | Specialized tooling, special test equipment (STE), and special inspection equipment (STI) needs/requirements identified for material and/or process family/class specimen testing required to support hypothesis development to establish qualitative cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Specialized tooling, special test equipment (STE), and special inspection equipment (STI) needs/requirements identified for device family hardware testing required to support hypothesis validation to establish quantitative correlations between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Specialized tooling, special test equipment (STE), and special inspection equipment (STI) needs/requirements identified for part family component testing required to support analytical model development and validation for the quantitative prediction of cause-effect relationships between critical technology variables and design dependent parameters (e.g., producibility, manufacturability, material maturity, process maturity). | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered for system concepts under consideration as part of AoA. Tooling/STE/STI development and validation needs for preferred system concepts identified and incorporated into the Systems Engineering Plan (SEP).
MDD
A

## SE-TRL-MRL Gate Focus
|  | Early Development Planning |  |  | ASR | SRR/SFR | PDR | CDR
|  | Gate 1 | Gate 2 | Gate 3 | Gate 4 | Gate 5 | Gate 6 | Gate 7
| SE Focus (Outcome) | Gate 1: Knowledge of User Needs for New Capabilities (Product & Production Systems); Gate 4: System Solution Development to Provide New Capabilities (Product & Production Systems); Gate 7: Configuration Item Development
| SE Focus (Artifacts) | Operational-Level Needs 8-20 Years in the Future to Address Operational Shortcomings Already Experiences (CONOPS Description) | Identification and Prioritization of Specific Capability Gaps and Recommendations for Potential Types of Solutions to Address (Capability Based Assessment) | Analysis of Operational Risk Associated with Capability Gaps and Identifications of Potential Solution Approaches (Initial Capabilities Document) | Broad Spectrum of Alternative System Solution Concepts Evaluated with a Prefrerred System Concept Identified (Analysis of Alternatives) | System Performance Specification and Functional Baseline Established that Define "Technical" Requirements | Item Performance Specifications and Allocated Baseline Established that Define "Design to" Requirements | Item Detail, Material, and Process Specifications along with Product Baseline Established that Define "Build to" Requirements
\ | TRL Focus (Outcome) | Gate 1: Knowledge of Technological Capability Needs and Gaps (Product Systems); Gate 4: Technology Development to Address Capability Shortfalls (Product Systems); Gate 7: Product Line Development
| TRL Focus (Environment) | Paper/Laboratory | Paper/Laboratory | Paper/Laboratory | Laboratory | Operationally Relevant | Operationally Relevant | Operational
| TRL Focus (Applications) | Gate 1: Improved Understanding of Physical Phenomena that can be Linked to Material and/or Process Families/Classes; Gate 2: Practical Applications of Technology Invented that can be Linked to Generic Device Family Applications; Gate 3: Proof-of-Concept of Individual Technology Elements that can be Linked to Dinstinctive Part Family Applications; Gate 4: Integration of Basic Technology Components for Concepts that can be Linked to Distinctive Product Family Applications
| TRL Focus (Methods) | Descriptive Studiesto Generate Hypotheses that Characterize the Who, Where, and When in Relation to the What (Critical Variables) | Analytic Studies that Test Hypotheses and Define the Why and How in Relation to the What through Cause-Effect Correlations (Design Dependent Parameters) | Anaytical Predictive Models and Experimental Sudies using Non-Integrated Low-Fidelity Component Hardware (Critical Functions) | Low-Fidelity Components and/or Breadboard Hardware Demonstration and Validation (All Functions) | High-Fidelity Components and/or Breadboard Hardware Development and Validation (Function, ~Form, ~Fit) | Prototype System, Subsystem, Assembly, and/or Component Development and Validation (Fit, Form, Function) | Prototype System, Subsystem, Assembly, and/or Component Development and Validation (Fit, Form, Function)
| MRL Focus (Outcome) | Gate 1: Knowledge of Industrial Capability Needs and Gaps (Production Systems); Gate 4: Industrial Base Development to Address Capability Shortfalls (Production Systems); Gate 7: Production Line Development
| MRL Focus (Environment) | Paper/Laboratory | Paper/Laboratory | Paper/Laboratory | Laboratory | Production Relevant | Production Relevant | Production Representative
| MRL Focus (Capabilities) | Gate 4: Capability to Produce Technology in a Laboratory Environment; Gate 5: Capability to Produce Prototype Components in a Production Relevant Environment; Gate 6: Capability to Produce a Prototype System or Subsystem in a Production Relevant Environment; Gate 7: Capability to Produce Systems, Subsystems, and Components in a Production Representative Environment
NOTE: Descriptive Studies Generate Hypotheses and Answer "WHO"," WHERE", and "WHEN" in Relation to the "WHAT" or Outcome
NOTE: Analytic Studies Test Hypotheses and Answer the "WHY" and "HOW" by Establishing Input-Output Relationship Between Critical Parameters
NOTE: Analytical Models Predict Phenomena Using Y=F(X) Correlations for Critical Functions and/or Characteristics to Answer "HOW WELL"
NOTE: Low-Fidelity Breadboards Resemble the Final End Item in Function Only
NOTE: High-Fidelity Breadboards Resemble the Final End Item in both Function and the Approximate Physical Configuration or Form and Fit
NOTE: Prototypes are Physical or Virtual Models that Resemble the Final End Item in Fit, Form, and Function
NOTE: Production Relevant Environments Provide some Shop Floor Realism (Facilities, Personnel, Tooling, Processes, Materials, etc.)
NOTE: Production Representative Environments Provide as much Production Realism as Possible and should Resemble Acual Industrial Pilot Lines
NOTE: Operational Needs Define "WHAT" Functions must be Performed, "WHEN" they are Performed, "WHO" will Perform them, and "WHERE they will be Performed
NOTE: Concept of Operations Describes "HOW" the Set of Proposed Capabilities can be Employed to Achieve the Desired Objectives or End State
NOTE: Functional Requirements Define "WHAT" the System/Solution Must Accomplish in Terms of Tasks and Activities Independent of the Solution Approach
NOTE: Performance Requirements Define "HOW WELL" the System/Solution Must Accomplish its Objective without Prescribing any Preferred Approach
NOTE: End Items Refer to a Unique Product Family, Process, and Material Combination used to Produce a Component, Assembly, Subsystem, or System
A
B
MDD

## MRL WS Oct 2017 Proposed
|  | MRL 1 | MRL 2 | MRL 3 | MRL 4
A.1 Industrial Base | Existing |  |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
| Proposed |  |  | Understand the state of the art. Potential sources identified to address capability needs for concepts under consideration. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
A.2 Manufacturing Technology Development | Existing |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified.
| Proposed |  | Manufacturing Science (concepts, technologies, and capabilities) requirements identified to support potential solutions. | Advanced manufacturing technology concepts and capbilities identified. | Advanced manufacturing technology development requirements identified.
B.1 Producibility Program | Existing |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
| Proposed |  | Identify potential elements of the concept (materials, processes, capabilities, limitations) that impact producibility. | Relevant elements evaluated for producibility using experiments, models and simulations. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
B.2 Design Maturity | Existing | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
| Proposed | Manufacturing research opportunities identified. | Manufacturing and technical requirements identified that may drive manufacturing options. Broad performance goals identified. | Top level product performance, lifecycle, and technical requirements defined and evaluated. Trade-offs in design options assessed based on experiments. | Form, fit, and function constraints identified and manufacturing capabilities identified for preferred system concepts. SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified.
C.1 Production Cost Knowledge | Existing |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
| Proposed |  | Cost model approach defined. | Initial cost models developed for process steps and materials (high-level process chart). Manufacturing cost estimates for potential solutions initiated. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
C.2 Cost Analysis | Existing | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
| Notes: | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to refine and quantify cost drivers, risks, and development strategy (e.g., lab to pilot line to factory). | Producibility and lifecycle cost risks assessed. Initial cost analysis supports Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
C.3 Manufacturing Investment Budget | Existing | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
| Proposed | Potential manufacturing investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.1 Maturity | Existing | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
| Proposed | Material characteristics and properties surveyed and identified for research. | Material properties and characteristics predicted based on research. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
D.2 Availability | Existing |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated.
| APT Proposed |  | Materials sources and availability identified. | Material availability and sourcing assessed. Material scale-up risks evaluated. | Projected lead times have been analyzed. All difficult to obtain, difficult to process, or hazardous materials have been identified. Quantity and lead time estimated.
D.3 Supply Chain Management | Existing |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources.
| Proposed |  |  | Initial assessment of potential supply chain capability. | Supply chain capabilities analyzed with gaps and risks identified for preferred concept.
D.4 Special Handling | Existing |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified.
| Proposed |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Potential special handling concerns and regulatory requirements assessed. Special handling procedures assessed. | List of hazardous materials updated. Special handling risks and issues identified. Special handling procedures are being followed.
E.1 Modeling & Simulation | Existing |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified.
| Proposed |  | Initial models developed, if applicable. | Modeling and simulations utilized to model behavior/performance of potential manufacturing solutions and define manufacturing concepts. | Production modeling/simulation approaches for process or product are identified.
E.2 Manufacturing Process Maturity | Existing |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes.
| Proposed |  | Identification of potential processing approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Current state of key/critical processes assessed against program requirements.
E.3 Process Yields and Rates | Existing |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
| Proposed |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
F.1 Quality Management | Existing |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Proposed |  |  |  | Quality management strategy included in technology development and in systems engineering activities.
F.2 Product Quality | Existing |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Proposed |  |  | Initial product quality requirements and risks identified. Inspection technologies identified. | Product inspection and acceptance testing strategy identified as part of the technology development and systems engineering activities.
F.3 Supplier Quality Management | Existing |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
| Proposed |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
G.1 Manufacturing Workforce | Existing |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
| Proposed |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) | Existing |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA.
| Proposed |  |  |  | Tooling, Special Test Equipment (STE), Special Inspection Equipment (SIE) requirements, including modifications, funding, and schedule, are considered as part of AoA.
H.2 Facilities | Existing |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA.
| Proposed |  |  | Specialized facility requirements/needs identified. | Capability and availability of manufacturing facilities for prototype development and production evaluated as part of trade studies or AoA.
I.1 Manufacturing Planning & Scheduling | Existing |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
| Proposed |  |  | Manufacturing concepts and systems to support trade studies identified. Manufacturing strategy development (notional plans and schedules) initiated. | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
I.2 Materials Planning | Existing |  |  |  | Technology development article component list developed with associated lead time estimates.
| Proposed |  | Initial plans and strategies for potential materials identified. | Specific condsiderations (availability, lead time, handling, storage) for the materials and components analyzed. | Materials and components list developed with estimates of availability, lead time, handling, storage, etc.

## Team 1 Proposed
| Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4
A.1 Industrial Base | Existing |  |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
|  |  |  | Understand the state of the art. Potential sources identified to address capability needs for concepts under consideration. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
A.2 Manufacturing Technology Development | Existing |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified.
| APT Proposed |  | Manufacturing Science (concepts, technologies, and capabilities) requirements identified to support potential solutions. | Advanced Manufacturing Technology concepts and capbilities capabilities identified. | Advanced Manufacturing Technology development requirements identified.
B.1 Producibility Program | Existing |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
|  |  | Identify potential characteristics of the concept (e.g. materials, processes, capabilities, limitations, etc.) that impact producibility. | Relevant materials and processes evaluated for producibility using experiments, models and simulations. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
B.2 Design Maturity | Existing | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
| Notes: | Manufacturing research opportunities identified. | Manufacturing and technical requirements identified that may drive manufacturing options. Broad performance goals identified. | Top level product performance, lifecycle, and technical requirements defined and evaluated. Trade-offs in design options assessed based on experiments. | Form, fit, and function constraints identified and manufacturing capabilities identified for preferred system concepts. SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified.
C.1 Production Cost Knowledge | Existing |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
| APT Proposed |  | Cost model approach defined. Initial cost targets and risks identified. Cost model defined (initial process chart). | Initial cost models developed for process steps and materials (high-level process chart). Manufacturing cost estimates for potential solutions initiated. | Cost models include manufacturing, materials, and special requirements cost drivers. Cost models driven by process variables (detailed process chart). Cost driver uncertainties quantified. Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
C.2 Cost Analysis | Existing | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
| Notes: | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to refine define and quantify cost drivers, risks, and development strategy (e.g., lab to pilot line to factory). | Producibility and lifecycle cost risks assessed. Initial cost analysis supports Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
C.3 Manufacturing Investment Budget | Existing | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
| Jim's | Potential manufacturing investments identified. | Based on identified cost elements and risks, projects have reasonable manufacturing budget estimates to meet project goals. Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Based on analysis, projects have reasonable manufacturing budget estimates for reaching MRL 4. Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place. Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.1 Maturity | Existing | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
| Jim's | Material characteristics and properties surveyed and identified for research. | Material properties defined based on research (literature, development, experiments, etc.). Material properties and characteristics predicted based on research. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
D.2 Availability | Existing |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated.
| APT Proposed |  | Materials sources and availability identified. | Material availability and sourcing assessed. Material scale-up risks evaluated. Quantities and lead times estimated. | Projected lead times have been analyzed. Identify all All difficult to obtain, difficult to process, or hazardous materials have been identified. Quantity and lead time risks determined.
D.3 Supply Chain Management | Existing |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources.
| Jim's |  | Potential suppliers supply chain materials sources identified. | Initial assessment of potential supply chain, including capacity, capability, and sourcing conducted. | Supply chain capabilities analyzed with gaps and risks identified for preferred concept.
D.4 Special Handling | Existing |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified.
| Jim's |  | Initial review and evaluation conducted of potential regulatory requirements and special handling concerns for applicability. (Working in ESH/EHS session) | List of hazardous materials identified. Potential special handling concerns and regulatory requirements assessed. Special handling procedures applied. (Working in ESH/EHS session) | List of hazardous materials updated. Special handling risks and issues identified. Special handling procedures are being followed. (Working in ESH/EHS session)
E.1 Modeling & Simulation | Existing |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified.
| Jim's | Identify potential modeling and simuluation approaches. | Initial models Models and simulations developed to support analysis of the project/concept. | Modeling and simulations utilized to model behavior/performance of potential manufacturing solutions and define manufacturing concepts. | Modeling and simulations of manufacturing concepts are finalized. Production modeling/simulation approaches for process or product are identified.
E.2 Manufacturing Process Maturity | Existing |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes.
| Jim's |  | Identification of material and/or process approaches. | High level manufacturing processes documented. Feasibility assessments/experimenation conducted identifying key/critical manufacturing processes and risks. | Complete an assessment to determine the current state of key/critical processes. Current state of key/critical processes assessed against program requirements.
E.3 Process Yields and Rates | Existing |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
| Jim's |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
F.1 Quality Management | Existing |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  | Potential quality management risks identified. | Identify quality management strategy requirements that address initial needs and metrics. | Quality management strategy included in technology development and in systems engineering activities.
F.2 Product Quality | Existing |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  |  | Initial product quality requirements and risks identified. Inspection technologies identified. | Product inspection and acceptance testing strategy identified as part of the technology development and systems engineering activities.
F.3 Supplier Quality Management | Existing |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
| Jim's |  |  | Supplier Quality Management processes identified that address quality management needs and metrics. | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
G.1 Manufacturing Workforce | Existing |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
| Jim's |  |  | Identify workforce requirements, including new skills, unique, challenging, special skills, and training requirements. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) | Existing |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA.
| APT Proposed |  |  | Requirements for tooling and/or capital equipment for existing and new manufacturing processes identified. | Tooling, Special Test Equipment (STE), Special Inspection Equipment (SIE) requirements, including modifications, funding, and schedule, are considered as part of AoA.
H.2 Facilities | Existing |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA.
| APT Proposed |  |  | Assess Facilities under consideration for capabilities. Specialized facility requirements/needs identified. | Capability, and availability of manufacturing facilities for prototype development and production evaluated as part of trade studies or AoA.
I.1 Manufacturing Planning & Scheduling | Existing |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
| APT Proposed |  |  | Manufacturing concepts and systems to support trade studies identified and manufacturing strategy development (notional plans and schedules) initiated. Manufacturing concepts and systems to support trade studies identified. Manufacturing strategy development (notional plans and schedules) initiated. | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
I.2 Materials Planning | Existing |  |  |  | Technology development article component list developed with associated lead time estimates.
| APT Proposed |  | Manufacturing considerations (planning and strategy ) for potential materials identified. Initial plans and strategies for potential materials identified. | Specific condsiderations (availability, lead time, handling, storage, etc.) for the materials and components analyzed. Specific considerations (e.g. availability, lead time, handling, storage) for the materials and components analyzed. | Materials and components list developed based on estimates of availability, lead time, handling, storage, etc.
Note on F35: Author: The original MRL 4 Criteria did not change
Note on F41: Author: remove comma

## Team 2 Matrix v11.6
Version 11.6 | 2016-08-01
DoD Manufacturing Readiness Levels (MRLs)
Acquisition Phase |  | Pre Materiel Solution Analysis (Pre MSA) |  |  | Materiel Solution Analysis (MSA) | Technology Maturation and Risk Reduction (TMRR) |  | Engineering & Manufacturing Development (EMD) |  | Low-Rate Initial Production (LRIP) | Full-Rate Production (FRP)
Technical Reviews |  |  |  |  | ASR | SRR/SFR | PDR | CDR | PRR/SVR | PCA
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | D.4 - Special Handling (i.e. Government Furnished Property (GFP), shelf life, security, hazardous materials, storage environment, ESH, etc.) |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified and alternatives evaluated. Special handling procedures, including environmental, safety, and health, applied in the lab with established disposal procedures. Special handling concerns assessed. | List of hazardous materials updated and alternatives assessed. Special handling procedures, including environmental, safety, and health, applied in the lab and disposal procedures evaluated. Special handling requirements identified and analyzed. | Special handling procedures, including environmental, safety, and health, applied in production relevant environment. Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. Waste stream (disposal/recycle) analysis initiated. | Special handling procedures, including environmental, safety, and health, applied in production relevant environment. Plans to address special handling requirement gaps complete. Manufacturing assessed for material storage and waste handling risks. | Special handling procedures, including environmental, safety, and health, applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. Hazardous material storage and disposal plan in place for the pilot line. | Special handling procedures, including environmental, safety, and health, applied in pilot line environment. Special handling procedures demonstrated in EMD or Technology Insertion Programs. Special handling issues pose no significant risk for LRIP. All work instructions contain special handling provisions as required. Hazardous material storage and disposal plan evaluated and in place for LRIP. | Special handling procedures, including environmental, safety, and health, applied in LRIP environment. Special handling and hazardous material storage and disposal procedures demonstrated in LRIP. Special handling and hazardous material storage and disposal issues pose no significant risk for FRP. | Special handling procedures, including environmental, safety, and health, effectively implemented in FRP.
H - Facilities | H.2 - Facilities |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA. Human Factors & Ergonomics /Safety requirements identified and assessed for manufacturing personnel. | Manufacturing facilities identified and plans developed to produce prototypes. Human Factors & Ergonomics /Safety requirements identified and assessed for manufacturing personnel. | Manufacturing facilities identified and plans developed to produce pilot line build. Human Factors & Ergonomics /Safety requirements verified in a production relevant environment for manufacturing personnel. | Manufacturing facilities identified and plans developed to produce LRIP build. Human Factors & Ergonomics /Safety practices validated in a production relevant environment for manufacturing personnel. | Pilot line facilities demonstrated. Manufacturing facilities adequate to begin LRIP. Plans in place to support transition to FRP. Workplace safety is adequate. Human Factors & Ergonomics /Safety practices demonstrated on a pilot line for manufacturing personnel. | Manufacturing facilities in place and demonstrated in LRIP. Capacity plans adequate to support FRP. Human Factors & Ergonomics /Safety practices demonstrated in LRIP for manufacturing personnel. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Human Factors & Ergonomics /Safety requirements demonstrated in FRP and updated for manufacturing personnel.
A
FRP
C
B

## Team 2 Matrix Transposed
| MRLWG Proposed Language |  | Proposed Alternative | Industry Developed Additional Thread |  |  | Boeing Questions |  |  | Northrop Questions
Thread | D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | H - Facilities | D - Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | J - Environmental Health and Safety
Sub-Thread | D.4 - Special Handling | H.3- ESH Management | D.4 - ESH & Special Handling | J.1 - Materials | J.2 - Infrastructure | J.3 - Administrative | Materials | Infrastructure | Administrative
MRL 1 |  |  |  | Are Documented Safety Data Sheet (SDS) available for known raw materials?
MRL 2 | Initial evaluation of potential regulatory requirements and special handling concerns. |  | Initial evaluation of potential ESH requirements and special handling concerns. | Are Safety Data Sheets (SDS) evaluations for compatibility and segregation requirements initiated? |  |  | Do any identified material transformational process create a new or unknown safety risk?
MRL 3 | List of hazardous materials identified and alternatives evaluated. Special handling procedures, including environmental, safety, and health, applied in the lab with established disposal procedures. Special handling concerns assessed. |  | ESH compliance risk identified. List of hazardous materials identified. Special handling procedures applied in the lab with established disposal procedures. Special handling concerns assessed. | Have all materials been assessed for EHS risks?-…..specifically have you checked out alternatives and how they can impact the life cycle (womb to tomb) of the product? |  |  |  |  | Has potential risk categories been identified, based on the current manufacturing concepts? (Hazardous Energy, Ordinance, Vehicle/Pedestrian interaction, Machine/Operator interactions, Confined Space, Working from Heights, Crane Operations, Hazardous Machine Operations, Chemical Process Management, Towing) | Perhaps disposal procedures should be initiated or drafted, but established is a reach for us. More typical question we are asking at this stage is "Are there unique infrastructure requirements for new materials identified?" Evaluation of permit and licensing requirements for new materials is also a more typical question for us at this stage.
MRL 4 | List of hazardous materials updated and alternatives assessed. Special handling procedures, including environmental, safety, and health, applied in the lab and disposal procedures evaluated. Special handling requirements identified and analyzed. | Human Factors & Ergonomics /Safety requirements identified for manufacturing (personnel, processes & equipment). | ESH compliance risk mitigated in lab environment. List of hazardous materials updated. Special handling procedures applied in the lab and disposal procedures evaluated. Special handling requirements identified and analyzed. | Has the EHS representative and Value Stream evaluated reuse/recycle of material stream in house and at the supplier? |  |  | Is the hazardous/prohibited material list current for use in lab? | Is a laboratory safety plan/procedures in place. | Has a initial safety review been preformed for the handling and storage of the materials to be used in the laboratory environment? | Would disposal procedures be evaluated after they are established? HF&E requirements are not necessarily fully identified and assessed at this time. Ergonomics evaluation typically comes much later for us (during pilot line).
MRL 5 | Special handling procedures, including environmental, safety, and health, applied in production relevant environment. Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. Waste stream (disposal/recycle) analysis initiated. | Human Factors & Ergonomics /Safety requirements assessed for manufacturing (personnel, processes & equipment). | ESH requirements and special handling procedures applied in production relevant environment. Special handling requirement gaps identified. Only new special handling processes demonstrated in lab environment. | Has the waste stream analysis been initiated and have reuse/recycle projects been initiated for all materials capable of recycle? | Have EHS (special medical /ergonomic requirements, alternate energy) issues been assessed for preferred manufacturing process? | Has initial safety risk assessment (SRA) been completed for preferred manufacturing process? |  | Are all new enabling/critical safety technologies and components identified? (i.e.. Lock-Out Tag-Out)
MRL 6 | Special handling procedures, including environmental, safety, and health, applied demonstrated in production relevant environment. Plans to address special handling requirements gaps, risks, and issues complete. Manufacturing assessed for material storage and waste handling risks/issues. | Human Factors & Ergonomics /Safety requirements verified in a production relevant environment | ESH requirements addressed and documented. Special handling procedures, applied in production relevant environment. Plans to address special handling requirement gaps complete. Manufacturing assessed for material storage and waste handling risks. | Have manufacturing sites' EHS function assessed material storage and waste handling issues? | Have manufacturing sites' EHS function assessed ergonomic issues? | Has safety risk assessment (SRA) for equipment used in preferred manufacturing process been updated? |  | Is an Accident/Incident data collection process in place and active for prototype testing Have all designs been evaluated for access in both production and maintenance safety
MRL 7 | Special handling procedures, including environmental, safety, and health, applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. Hazardous materials storage and disposal plan in place for the pilot line. | Human Factors & Ergonomics /Safety practices validated in a production relevant environment. | Demonstrate ESH compliance in production representative environment. Special handling procedures, applied in production representative environment. Special handling procedures developed and annotated on work instructions for pilot line. Hazardous material storage and disposal plan in place for the pilot line. | Have manufacturing sites' EHS function assessed hazardous materials and applied for all required permits? | Has the ergonomics needs for workstations and operators been addressed? | Has safety risk assessment (SRA) been completed and associated risk mitigation strategies established? |  | Has Lock-Out Tag-Out LOTO process and equipment been demonstrated? Is accident/incident data being addressed and the effectiveness of mitigation measures reviewed and verified?
MRL 8 | Special handling procedures, including environmental, safety, and health, applied in pilot line environment. Special handling procedures demonstrated in EMD or Technology Insertion Programs. Special handling issues pose no significant risk for LRIP. All work instructions contain special handling provisions as required. Hazardous material storage and disposal plan evaluated and in place for LRIP. | Human Factors & Ergonomics /Safety practices demonstrated on a pilot line. | Demonstrate ESH compliance in pilot line production. Special handling procedures handling procedures demonstrated in EMD or Technology Insertion Programs. Special handling issues pose no significant risk for LRIP. All work instructions contain special handling provisions as required. Hazardous material storage and disposal plan evaluated and in place for LRIP. | Have manufacturing sites' EHS function established hazardous materials disposal requirements? | Have manufacturing sites' EHS function refined all IH/toxicology and ergonomic requirements for production? | Have safety risk assessment (SRA) issues been mitigated and EHS training program established? |  | Have all essential safety data (i.e. fall protection plans, SDS sheets, Hazardous energy plans, etc.) been created, released, and available to productions? | Have all high severity health and safety issues been resolved or mitigated to acceptable levels? (Hazardous Energy, Ordinance, Vehicle/Pedestrian interaction, Permit Required Confined Space, Working from Heights, Crane Operations, Hazardous Machine Operations, Chemical Process Management, Towing)
MRL 9 | Special handling procedures, including environmental, safety, and health, applied in LRIP environment. Special handling and hazardous material storage and disposal procedures demonstrated in LRIP. Special handling and hazardous material storage and disposal issues pose no significant risk for FRP. | Human Factors & Ergonomics /Safety practices demonstrated in LRIP. | Demonstrate ESH compliance in LRIP. Special handling procedures, applied in LRIP environment. Special handling and hazardous material storage and disposal procedures demonstrated in LRIP. Special handling and hazardous material storage and disposal issues pose no significant risk for FRP. | Have manufacturing sites' EHS function established hazardous materials storage and disposal requirements? | Have manufacturing sites' EHS function refined all IH/toxicology and ergonomic requirements for production? | Has the SRA been completed including the installation of safety engineering/isolation systems? Asbestos HP02, Floor Sealers & Coatings EP04, Safety Showers& Eyewash Station SP11, Evacuation & Refuge Plan |  | Has an audit schedule been incorporated into the manufacturing plan for Safety and health process checks.
MRL 10 | Special handling procedures, including environmental, safety, and health, and hazardous material storage and disposal procedures effectively implemented in FRP. | Human Factors & Ergonomics /Safety requirements demonstrated in FRP. | Demonstrate ESH compliance in FRP. Special handling procedures effectively implemented in FRP. | Have the waste stream analysis projects been completed for all materials capable of reuse or recycle? Has material storage and disposal process been validated to plant procedures and permits? | Has the required PPE been verified that it can withstand production and fits all employees properly? | Has the EHS training been completed?
Note on B8: Author: Move to Users Guide
Note on B9: Author: Added "issues" in keeping with new guidance on Risks/Issues/Opportunities.
Note on B10: Author: Put specifics in Users Guide.
Note on K7: Author: The point of having HFE requirements identified could be simply the already documented company procedures for evaluating worker safety and ergonomics both on a periodic basis and for new machinery and equipment.

## Team 3 Proposed
| Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4
A.1 Industrial Base | Existing | Throughout these criteria, because of the brevity, it was generally felt that there was not enough specificity in the statements (and terms needing defined). This could be accomplished in the MRL Users Guide, but has to be released at the same time as these new criteria. In keeping with instructions, no changes were made, just comments. |  | Potential sources identified to address technology needs. Understand state of the art. | Industrial base capabilities surveyed and known gaps/risks identified for preferred concept, key technologies, components, and/or key processes.
Understand the state of the art. Potential sources identified to address capability needs for concepts under consideration.
A.2 Manufacturing Technology Development | Existing |  | New manufacturing concepts and potential solutions identified. | Manufacturing technology concepts identified through experiments/models. | Manufacturing Science & Advanced Manufacturing Technology requirements identified.
| APT Proposed |  | Manufacturing Science (concepts, technologies, and capabilities) requirements identified to support potential solutions. | Advanced manufacturing technology concepts and capbilities identified. | Advanced Manufacturing Technology development requirements identified.
B.1 Producibility Program | Existing |  |  | Relevant materials/processes evaluated for manufacturability using experiments/models. | Initial producibility and manufacturability assessment of preferred systems concepts completed. Results considered in selection of preferred design concepts and reflected in Acquisition Strategy key components/ technologies.
|  |  | Identify potential characteristics of the concept (materials, processes, capabilities, limitations, etc.) that impact producibility. | Relevant materials and processes evaluated for producibility using experiments, models and simulations.
B.2 Design Maturity | Existing | Manufacturing research opportunities identified. | Applications defined. Broad performance goals identified that may drive manufacturing options. | Top level performance requirements defined. Trade-offs in design options assessed based on experiments. Product lifecycle and technical requirements evaluated. | SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified. Form, fit, and function constraints identified and manufacturing capabilities identified for preferred systems concepts.
| Notes: |  | Manufacturing and technical requirements identified that may drive manufacturing options. Broad performance goals identified. | Top level product performance, lifecycle, and technical requirements defined and evaluated. Trade-offs in design options assessed based on experiments. | Form, fit, and function constraints identified and manufacturing capabilities identified for preferred system concepts. SEP and Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial potential Key Performance Parameters (KPPs) identified for preferred systems concept. System characteristics and measures to support required capabilities identified.
C.1 Production Cost Knowledge | Existing |  | Cost model approach defined. | Initial cost targets and risks identified. High level process chart model developed. Technology cost models developed for new process steps and materials based on experiments. | Manufacturing, material and special requirement cost drivers identified. Detailed process chart cost models driven by process variables. Cost driver uncertainty quantified.
| APT Proposed |  | Initial cost targets and risks identified. Cost model defined (initial process chart). | Initial cost models developed for process steps and materials (high-level process chart). Manufacturing cost estimates for potential solutions initiated. | Cost models include manufacturing, materials, and special requirements cost drivers. Cost models driven by process variables (detailed process chart). Cost driver uncertainties quantified.
C.2 Cost Analysis | Existing | Identify any manufacturing cost implications. | Cost elements identified. | Sensitivity analysis conducted to define cost drivers and production development strategy (i.e. lab to pilot to factory). | Producibility cost risks assessed. Initial cost models support Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
| Notes: |  |  | Sensitivity analysis conducted to refine and quantify cost drivers, risks, and development strategy (e.g., lab to pilot line to factory). | Producibility and lifecycle cost risks assessed. Initial cost analysis supports Analysis of Alternatives (AoA) and Alternative Systems Review (ASR).
C.3 Manufacturing Investment Budget | Existing | Potential investments identified. | Program/projects have reasonable budget estimates for reaching MRL 3 through experiment. | Program/projects have reasonable budget estimates for reaching MRL 4 by MS A. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
| Jim's | Potential manufacturing investments identified. | Based on identified cost elements and risks, projects have reasonable manufacturing budget estimates to meet project goals. | Based on analysis, projects have reasonable manufacturing budget estimates for reaching MRL 4. | Manufacturing technology initiatives identified to reduce costs. Program has reasonable budget estimate for reaching MRL 6. Estimate includes capital investment for production-relevant equipment. All outstanding MRL 4 risk areas understood with approved mitigation plans in place.
D.1 Maturity | Existing | Material properties identified for research. | Material properties and characteristics predicted. | Material properties validated and assessed for basic manufacturability using experiments. | Projected materials have been produced in a laboratory environment.
| Jim's | Material characteristics and properties surveyed and identified for research. | Material properties defined based on research (literature, development, experiments, etc.).
D.2 Availability | Existing |  | Material availability assessed. | Material scale-up issues identified. | Projected lead times have been identified for all difficult to obtain, difficult to process, or hazardous materials. Quantities and lead times estimated.
| APT Proposed |  | Materials sources and availability identified. | Material availability and sourcing assessed. Material scale-up risks evaluated. Quantities and lead times estimated. | Projected lead times have been analyzed. Identify all difficult to obtain, difficult to process, or hazardous materials. Quantity and lead time risks determined.
D.3 Supply Chain Management | Existing |  |  | Initial assessment of potential supply chain capability. | Survey completed for potential supply chain sources.
| Jim's |  | Potential supply chain materials sources identified. | Initial assessment of potential supply chain, including capacity, capability, and sourcing conducted. | Supply chain capabilities analyzed with gaps and risks identified for preferred concept.
D.4 Special Handling | Existing |  | Initial evaluation of potential regulatory requirements and special handling concerns. | List of hazardous materials identified. Special handling procedures applied in the lab. Special handling concerns assessed. | List of hazardous materials updated. Special handling procedures applied in the lab. Special handling requirements identified.
| Jim's |  | Initial review and evaluation conducted of potential regulatory requirements and special handling concerns for applicability. | List of hazardous materials identified. Potential special handling concerns and regulatory requirements assessed. Special handling procedures applied. | List of hazardous materials updated. Special handling risks and issues identified. Special handling procedures are being followed.
E.1 Modeling & Simulation | Existing |  | Initial models developed, if applicable. | Identification of proposed manufacturing concepts or producibility needs based on high-level process flow chart models. | Production modeling/simulation approaches for process or product are identified.
| Jim's |  | Models and simulations developed to support analysis of the project/concept. | Modeling and simulations utilized to model behavior/performance of potential manufacturing solutions and define manufacturing concepts. | Modeling and simulations of manufacturing concepts are finalized.
E.2 Manufacturing Process Maturity | Existing |  | Identification of material and/or process approaches. | Document high level manufacturing processes. Critical manufacturing processes identified through experimentation. | Complete a survey to determine the current state of critical processes.
| Jim's |  |  | Feasibility assessments conducted identifying key/critical manufacturing processes and risks. | Complete an assessment to determine the current state of key/critical processes.
E.3 Process Yields and Rates | Existing |  |  | Initial estimates of yields and rates based on experiments or state of the art. | Yield and rates assessment on proposed/similar processes complete and applied within Analysis of Alternatives (AoA).
Jim's
F.1 Quality Management | Existing |  |  |  | Quality strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  | Potential quality management risks identified. | Identify quality management strategy requirements that address initial needs and metrics. | Quality management strategy included in technology development and in systems engineering activities.
F.2 Product Quality | Existing |  |  |  | Product inspection and acceptance testing strategy identified as part of the Acquisition Strategy and included in Systems Engineering Plan (SEP).
| Jim's |  |  | Initial product quality requirements and risks identified. | Product inspection and acceptance testing strategy identified as part of the technology development and systems engineering activities.
F.3 Supplier Quality Management | Existing |  |  |  | Potential supplier base quality capabilities and risks identified, including subtier supplier quality management.
| Jim's |  |  | Supplier Quality Management processes identified that address quality management needs and metrics.
G.1 Manufacturing Workforce | Existing |  |  | New manufacturing skills identified. | Manufacturing skill sets identified and production workforce requirements (technical and operational) evaluated as part of AoA. Determine availability of process development workforce for the Technology Maturation and Risk Reduction Phase.
| Jim's |  |  | Identify workforce requirements, including new skills, unique, challenging, special skills, and training requirements.
H.1 Tooling / Special Test and Inspection Equipment (STE/SIE) | Existing |  |  |  | Tooling/Special Test Equipment (STE)/Special Inspection Equipment (SIE) requirements are considered as part of AoA.
| APT Proposed |  |  | Requirements for tooling and/or capital equipment for existing and new manufacturing processes identified. | Tooling, Special Test Equipment (STE), and Special Inspection Equipment (SIE) requirements including modifications, funding, and schedule are considered as part of AoA.
H.2 Facilities | Existing |  |  | Specialized facility requirements/needs identified. | Availability of manufacturing facilities for prototype development and production evaluated as part of AoA.
| APT Proposed |  |  | Assess facilities under consideration for capabilities. | Capability and availability of manufacturing facilities for prototype development and production builds evaluated as part of trade studies or AoA.
I.1 Manufacturing Planning & Scheduling | Existing |  |  |  | Manufacturing strategy developed and integrated with acquisition strategy. Prototype schedule risk mitigation efforts incorporated into Acquisition Strategy.
| APT Proposed |  |  | Manufacturing concepts and systems to support trade studies identified and manufacturing strategy development (notional plans and schedules) initiated.
I.2 Materials Planning | Existing |  |  |  | Technology development article component list developed with associated lead time estimates.
| APT Proposed |  | Manufacturing considerations (planning and strategy ) for potential materials identified. | Specific considerations (availability, lead time, handling, storage, etc.) for the materials and components analyzed. | Materials and components list developed based on with estimates of availability, lead time, handling, storage, etc.
Note on D25: Author: Questions about if we should keep "if applicable". Should we specify physics based models as an example or trade space models, or computational models.
Note on D31: Author: Comment was I can't manage quality in an area where there are no specs. No value for quality management here
Note on E10: Author: Use of "technology" here is not clear needs definition.
Note on E35: Author: DoD doesn’t always allow resources to be available for this doing this at this time.
Note on E37: Author: is this the workforce in the lab or production define the skills to make the parts
Note on E39: Author: What kind of requirements? General requirements ROM System level requirements? High level requirements? NEED SPECIFICITY!
Note on E41: Author: New capabilities specialized capabilities are we losing the focus on the potential risks production or prototype facilities? What type of facilities?
Note on F25: Author: Models should be of three things: product, performance, or process
Note on F27: Author: Strong reactions about including definitions in the Users Guide.
Note on F39: Author: Should this be stated as trade studies, or include trade studies? Definitions of what is meant by an AoA as a uniform definition should be in the deskbook and consistent throughout the thread.