## First
Version 6.4 | 2008-05-10
DoD Manufacturing Readiness Levels (MRLs)
S&T Phase |  | 6.1 Basic Research | 6.2 Applied Research | 6.2 / 6.3 | 6.3 / 6.4 | 6.3 / 6.4 / 7.8 | 6.4 / 6.8 / 7.8 | 7.8 | 7.8 | 7.8 | 7.8 Title III
Acq Phase |  | Pre CR | Pre CR | Pre CR | CR - MS A | TD | MS B | SDD | MS C | LRIP - FRP | FRP
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
Technology & Industrial Base | Technology Maturity | Should be assessed at TRL 1. | Should be assessed at TRL 2. | Should be assessed at TRL 3. | Should be assessed at TRL 4. | Should be assessed at TRL 5. | Should be assessed at TRL 6. | Should be assessed at TRL 7 | Should be assessed at TRL 7. | Should be assessed at TRL 8. | Should be assessed at TRL 9.
| Technology Transition to Production |  | New technology approaches defined. | Potential manufacturing sources identified for technology needs. (Commercial/Government, Domestic/Foreign) | Industrial Base capabilities and gaps/risks identified for key technologies, components, and/or key processes. | Industrial Base assessed to identify potential manufacturing sources. | Industrial Capability Assessment (ICA) for MS B has been completed. Industrial capability in place to support mfg of development articles. Plans to minimize sole/foreign sources complete. Need for sole/foreign sources justified. Potential alternative sources identified. | Industrial capability to support production has been analyzed. Sole/foreign sources stability is assessed/monitored. Developing potential alternate sources as necessary. | Industrial Capability Assessment (ICA) for MS C has been completed. Industrial capability is in place to support LRIP. Sources are available, multi-sourcing where cost-effective or necessary to mitigate risk. | Industrial capability is in place to support start of FRP. | Industrial capability supports FRP. Industrial capability assessed to support mods, upgrades, surge and other potential manufacturing requirements.
| Manufacturing Technology Development |  | New manufacturing approaches defined. | Initial demonstration of manufacturing concept conducted. | Mfg Science & Advanced Mfg Technology requirements identified | Required manufacturing technology development efforts initiated. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production relevant environment. | Manufacturing technology efforts continuing. Required manufacturing technology development solutions demonstrated in a production representative environment. | Manufacturing technology efforts continuing. Required manufacturing technology solutions validated on a pilot line. | Manufacturing technology efforts continuing. Manufacturing technology process improvements efforts initiated for FRP. | Manufacturing technology efforts continuing. Manufacturing technology continuous process improvements ongoing.
Design | Producibility Program | Feasibility of materials/processes assessed. | Relevant material/process requirements defined. | Relevant materials/processes for manufacturability & producibility evaluated. | Producibility & Manufacturability assessment of design concepts completed. Results guide selection of design concepts and key components/technologies for Technology Development Strategy. Manufacturing Processes assessed for capability to test and verify in production, and influence on O&S. | Producibility & Manufacturability assessments of key technologies and components initiated. Systems Engineering Plan (SEP) requires validation of design choices against manufacturing process and industrial base capability constraints. | Producibility assessments of key technologies/components and producibility trade studies (performance vs. producibility) completed. Results used to shape System Development Strategy and plans for SDD or technology insertion programs phase. | Detailed producibility trade studies using knowledge of key design characteristics and related manufacturing process capability completed. Producibility enhancement efforts (e.g. DFMA) initiated. | Producibility improvements implemented on system. Known producibility issues have been resolved and pose no significant risk for LRIP. | Prior producibility improvements analyzed for effectiveness during LRIP. Producibility issues/risks discovered in LRIP have been mitigated and pose no significant risk for FRP. | On-going producibility improvements analyzed for effectiveness. Producibility refinements continue. All mods, upgrades, DMSMS and other changes assessed for producibility.
| Design Maturity | Top level trade-offs in design options assessed. | Maturity goals defined. | Product lifecyle requirements and product performance requirements evaluated. | Systems Engineering Plans and the Test and Evaluation Strategy recognize the need for the establishment/validation of manufacturing capability and management of manufacturing risk for the product lifecycle. Initial Key Performance Parameters (KPPs) identified. | Identification of enabling/critical technologies and components is complete and includes the product lifecycle. Evaluation of design Key Characteristics (KC) initiated. | Basic system design requirements defined. All enabling/critical technologies/components have been tested and validated. Product data required for prototype manufacturing released. A preliminary performance as well as focused logistics specification is in place. Key Characteristics and tolerances have been established. | Product requirements and features are well enough defined to support detailed systems design. All product data essential for manufacturing of component design demonstration released. Potential KC risk issues have been identified and mitigation plan is in place. Design change traffic may be significant. | Detailed design of product features and interfaces is complete. All product data essential for system manufacturing released. Major product design features are sufficiently stable such that key LRIP manufacturing processes will be representative of those used in FRP. Design change traffic does not significantly impact LRIP. Key characteristics are stable and have been demonstrated in SDD or technology insertion program. | Major product design features are stable and LRIP produced items are proven in product testing. Design change traffic is limited to minor configuration changes. All KC's are controlled in production to three sigma or other appropriate quality levels. | Product design is stable. Design changes are few and generally limited to those required for continuous improvement or in reaction to obsolesence. All KCs are controlled to six sigma or other appropriate quality levels.
Cost & Funding | Production Cost Knowledge (Cost modeling) |  |  | Technology cost models developed for new process steps and materials based on engineering details at MRL 1-2. High-level process chart cost models with major production steps identified at MRL 3. | Detailed process chart cost models driven by key characteristics and process variables. Manufacturing, material and specialized reqt. cost drivers identified. | Detailed end-to-end value stream map cost model for major system components includes Materials, Labor, Equipment, Tooling/STE, setup, yield/scrap/rework, WIP, and capability/capacity constraints. Component simulations drive cost models. | Cost model inputs include design requirements, material specifications, tolerances, integrated master schedule, results of system/subsystem simulations and production relevant demonstrations. | Cost models updated with detailed designs and features, collected quality data, plant layouts and designs, obsolescence solutions. | Engineering cost model driven by detailed design and validated with data from relevant environment. | Actual cost model developed for FRP environment. Variability experiments conducted to show FRP impact, potential for continuous improvement. | Cost model validated against actual FRP cost.
| Cost Analysis |  |  | Sensitivity, Pareto analysis to find cost drivers and production representative scenario analysis to focus S&T initiatives and address scale-up issues. | Material, manufacturing, and specialized reqt. costs identified for design concepts. Producibility cost risks assessed and manufacturing technology initiatives identified to reduce costs. | Current state analysis of cost of design choices, make/buy, capacity, process capability, sources, quality, key characteristics, yield/rate, and variability. | Cost analysis of mfg future states, design trades, supply chain/yield/rate/SDD/technology insertion plans. Allocate cost targets. Cost reduction and avoidance contract incentives identified. | Costs rolled up to system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction efforts underway, incentives in place. | Cost analysis of proposed changes to requirements or configuration. | LRIP cost goals met, learning curve validated. | FRP cost goals met. Cost reduction initiatives ongoing.
| Manufacturing Investment Budget |  |  | Program/ projects have budget estimates for reaching MRL of 4. | Program has budget estimate for reaching MRL 5. All Risk Mitigation Plans required to raise deficient elements to MRL of 4 are fully funded. | Program has budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for Production-representative equipment. All Risk Mitigation Plans required to raise deficient elements to MRL of 5 are fully funded. | Program has budget estimate for reaching MRL 7 by CDR. All Risk Mitigation Plans required to raise deficient elements to MRL of 6 are fully funded. | Program has budget estimate for reaching MRL 8 by MS C. Estimate includes investment for Low Rate Initial Production. All Risk Mitigation Plans required to raise deficient sub systems to MRL of 7 are fully funded. | Program has budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for Full Rate Production. All Risk Mitigation Plans required to raise deficient sub systems to MRL of 8 are fully funded. | Program has budget estimate for lean implementation during FRP. All Risk Mitigation Plans required to improve deficient subsystems to MRL of 9 during FRP are fully funded. | Production budgets sufficient for production at required rates and schedule.
Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | Maturity |  |  | Potential materials assessed for basic manufacturability. | Survey completed to determine if materials have been used before in a manufacturing environment. Preliminary plans in place to address producibility risks of new material. | Materials have been manufactured or produced in a prototype environment. Maturity efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place. | Materials maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated on System Demonstration and Development (SDD) production as adequate to support LRIP. Material specification stable. | Material is proven and controlled to specification in LRIP. | Material is proven and controlled to specification in FRP.
| Availability |  |  | New material scale-up issues assessed. | All exotic (difficult to obtain, process, or hazardous) materials identified. Lead times have been identified for all materials. | Availability issues addressed for prototype build. Significant material risks identified for all materials. Planning begun to address scale-up issues. | Availability issues addressed to meet technology demonstration articles. SDD long lead time items identified. Obsolescence issues identified. | Availability issues addressed to meet SDD builds. Long Lead procurement identified/planned for Low Rate Initial Production. Obsolescence plan in place. | Long Lead procurement initiated for LRIP. Availability issues pose no significant risk for LRIP. | Long Lead procurement initiated for Full Rate Production (FRP). Availability issues pose no significant risk for FRP. | Program is in FRP with no material availability issues.
| Supply Chain Management |  |  |  | Survey completed for potential supply chain sources. | Supply chain sources identified. Sole/single/foreign source vendors have been identified and planning has begun to minimize risks. | Supply chain plans in place (e.g., teaming agreements, etc.) leading to an SDD contract award. | Effective supply chain management process in place. Completed assessment of supply chain first tier. | Supply chain stable and adequate to support LRIP. Completed assessment of supply chain second tier. | Supply chain is stable and adequate to support FRP. Long term agreements in place where practical. | Supply chain proven and supporting FRP requirements.
| Special Handling (i.e. shelf life, security, hazardous materials, storage environment, etc.) |  |  | Potential special handling concerns identified. Materials Safety Data Sheets (MSDS) prepared as necessary. | Special handling requirements identified. MSDS reviewed and updated. | Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. | Plans to address special handling requirement gaps complete. | Special handling procedures developed. | Special handling procedures demonstrated on SDD or Technology insertion Programs production. Special handling issues pose no significant risk for LRIP. | Special handling procedures demonstrated in LRIP. Special handling issues pose no significant risk for FRP. | Special handling procedures effectively implemented in FRP.
Process Capability & Control | Modeling & Simulation (Product & Process) |  |  | Identification of proposed manufacturing concepts or producibility needs based on laboratory studies. | Production Modeling & Simulation approaches for Process or Product are identified. | Initial simulation models (product or process) developed at the component level. | Initial simulation models developed at the technology, sub-system or system level. | Simulation models used to determine system constraints and identify improvement opportunities. | Simulation models verified by SDD Article build, results used to improve process and determine that LRIP requirements can be met. | Simulation model verified by LRIP build, assist in management of LRIP and determine that FRP requirements can be met. | Simulation model verified by FRP build. Production simulation models used as tool to assist in management FRP.
| Manufacturing Process Maturity |  |  | Define Mfg State of the Art | Complete a survey to determine the current state of proposed processes. | Maturity has been assessed on similar processes in production. Process capability requirements have been identified. | Manufacturing processes demonstrated in production relevant environment. | Manufacturing processes demonstrated in a production representative environment. | Manufacturing processes verified for LRIP on a pilot line. Process capability data being collected or estimated. | Manufacturing processes & procedures are established and controlled in production to 3-sigma or other appropriate quality level. | Manufacturing processes & procedures are established and controlled in production to 6-sigma or other appropriate quality level.
| Process Yields and Rates |  |  |  | Yield and Rates assessment on proposed processes complete. | Target Yield and Rates established for production. Yield and Rate issues identified. Improvement plans initiated. | Yields and Rates evaluated in production relevant environment. Improvement plans on-going and updated. | Yields and Rates estimated in production representative environment. | Yields and Rates required to begin LRIP verified using SDD articles. | Yield and Rates targets achieved. Yield improvements on-going. | Yield and Rates targets achieved. Yield improvements on-going.
Quality Management | Quality Management including Supplier Quality. |  |  |  | Quality strategy identified as part of the Technology Development Strategy. | Quality Strategy refined in the System Engineering Plan and Key Charactaristic are Identified during Technology Demonstrations. | Initial Quality Plan and Quality Management System is in place. Quality Risks and Metrics have been identified. | Quality targets established. Demonstrate ability to collect and analyse quality data (process and system) in the production representative environment. | Quality targets demonstrated on pilot line. | Quality targets verified on production line. Continuous Quality Improvement begins. | Quality targets verified on production line. Continuous Quality Improvement on-going.
Mfg Personnel |  |  |  | Initial mfg skills identified. | Mfg skill sets identified to overcome production barriers | Skill sets identified to meet prototype production runs. Special skills certification and training requirements quantified | Mfg workforce skills available for production in a relevant environment. Training resources identified for production workforce. | Mfg workforce resource requirements identified for Pilot Line. Training resources identified for special skills deficiencies and LEAN Six Sigma Training | Mfg workforce resource requirements identified for LRIP. Ability of mfg workforce to produce repeatable products and workforce quality measured; training initiated for certification on special skills | LRIP personnel requirements met. FRP personnel requirements identified.. | FRP personnel requirements met. Production workforce skill sets maintained due to attrition of workforce.
Facilities |  |  |  | General industrial base (IB) capability identified for key technologies. | Specialized facility requirements/needs identified. | IB capabilities and gaps to support SDD and LRIP identified. Plan in place to fill gaps. | Mfg facility and facility development plans adequate to support SDD or Technology insertion Programs. | Facility capabilities for LRIP and FRP identified. Plan in place to fill gaps. Plant layout and design initiated. | Mfg facilities exist and are adequate to begin LRIP. Plans in place to support transition to FRP. | Mfg facilities in place and demonstrated in LRIP. and capacity plans adequate to support FRP decision. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Executable facilities surge plan available.
Mfg Management | Mfg Planning & Scheduling |  |  |  | Mfg strategy developed and integrated with acq strategy. Mfg risk mitigation efforts started. | Mfg strategy refined. Mfg risk mitigation efforts ongoing. | Initial mfg approach developed. All system design related mfg events included in Integrated Master Plan/Schedule. Mfg risk mitigation approach for SDD or Technology insertion Programs defined. | Initial Mfg Plan developed. Mfg risks integrated into Risk Mitigation Plan. | Mfg Plan Completed. All key manufacturing risks have been validated & mitigated using SDD or Technology Insertion Program work products. | Mfg Plan updated and validated for FRP. All manufacturing risks have been validated and mitigated using LRIP articles. | All manufacturing risks have been validated and mitigated using FRP articles.
| Materials Planning |  |  |  | Parts list in development with associated lead time calculations. | Parts list maturing, make/buy evaluations ongoing; lead times, quality, cost and other risks identified. | Most material decisions made (make/buy), material risk identified and plans made to mitigate. BOM initiated. | Analyses for Make/Buy decisions & BOM complete. Material planning systems in place for Pilot Line build. | Make/Buy decisions & BOM complete to support LRIP. Material planning systems validated on Pilot Line build. | Make/Buy decisions & BOM complete to support FRP. Material planning systems validated on LRIP build. | Program is in FRP with only process improvement/obsolescence make/buy or BOM changes allowed. Material Planning Systems validated on FRP build.
| Tooling / Special Test Equipment |  |  |  | Special Tooling / Special Test Equipment (STE) requirements are considered. | Identify Special Tooling /STE reqts & provide supporting rationale and schedule. | Prototype tooling concepts demonstrated in relevant mfg environment. | Production tooling and STE design and development efforts initiated. | All Tooling & Test Equipment proven on pilot line. Multiple tooling reqts identified for LRIP. | All Tooling & Test Equipment proven on LRIP. Multiple tooling reqts identified for FRP. | Proven Tooling & Test Equipment in place to support maximum FRP.

## Second
Version 6.4 | 2008-05-10
DoD Manufacturing Readiness Levels (MRLs)
S&T Phase |  | 6.1 Basic Research | 6.2 Applied Research | 6.2 / 6.3 | 6.3 / 6.4 | 6.3 / 6.4 / 7.8 | 6.4 / 6.8 / 7.8 | 7.8 | 7.8 | 7.8 | 7.8 Title III
Acq Phase |  | Pre CR | Pre CR | Pre CR | CR - MS A | TD | MS B | SDD | MS C | LRIP - FRP | FRP
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
Cost & Funding | Production Cost Knowledge (Cost modeling) |  | Cost model approach defined | Technology cost models developed for new process steps and materials based on engineering details at MRL 1-2. High-level process chart cost models with major production steps identified at MRL 3. | Detailed process chart cost models driven by key characteristics and process variables. Manufacturing, material and specialized reqt. cost drivers identified. | Detailed end-to-end value stream map cost model for major system components includes Materials, Labor, Equipment, Tooling/STE, setup, yield/scrap/rework, WIP, and capability/capacity constraints. Component simulations drive cost models. | Cost model inputs include design requirements, material specifications, tolerances, integrated master schedule, results of system/subsystem simulations and production relevant demonstrations. | Cost models updated with detailed designs and features, collected quality data, plant layouts and designs, obsolescence solutions. | Engineering cost model driven by detailed design and validated with data from relevant environment. | Actual cost model developed for FRP environment. Variability experiments conducted to show FRP impact, potential for continuous improvement. | Cost model validated against actual FRP cost.
| Cost Analysis |  | Cost elements identified. | Sensitivity, Pareto analysis to find cost drivers and production representative scenario analysis to focus S&T initiatives and address scale-up issues. | Material, manufacturing, and specialized reqt. costs identified for design concepts. Producibility cost risks assessed and manufacturing technology initiatives identified to reduce costs. | Current state analysis of cost of design choices, make/buy, capacity, process capability, sources, quality, key characteristics, yield/rate, and variability. | Cost analysis of mfg future states, design trades, supply chain/yield/rate/SDD/technology insertion plans. Allocate cost targets. Cost reduction and avoidance contract incentives identified. | Costs rolled up to system level and tracked against targets. Detailed trade studies and engineering change requests supported by cost estimates. Cost reduction efforts underway, incentives in place. | Cost analysis of proposed changes to requirements or configuration. | LRIP cost goals met, learning curve validated. | FRP cost goals met. Cost reduction initiatives ongoing.
| Manufacturing Investment Budget | Potential investment needs identified. | Program/ projects have budget estimates for reaching MRL of 3. | Program/ projects have budget estimates for reaching MRL of 4. | Program has budget estimate for reaching MRL 5. All Risk Mitigation Plans required to raise deficient elements to MRL of 4 are fully funded. | Program has budget estimate for reaching MRL 6 by MS B. Estimate includes capital investment for Production-representative equipment. All Risk Mitigation Plans required to raise deficient elements to MRL of 5 are fully funded. | Program has budget estimate for reaching MRL 7 by CDR. All Risk Mitigation Plans required to raise deficient elements to MRL of 6 are fully funded. | Program has budget estimate for reaching MRL 8 by MS C. Estimate includes investment for Low Rate Initial Production. All Risk Mitigation Plans required to raise deficient sub systems to MRL of 7 are fully funded. | Program has budget estimate for reaching MRL 9 by the FRP decision point. Estimate includes investment for Full Rate Production. All Risk Mitigation Plans required to raise deficient sub systems to MRL of 8 are fully funded. | Program has budget estimate for lean implementation during FRP. All Risk Mitigation Plans required to improve deficient subsystems to MRL of 9 during FRP are fully funded. | Production budgets sufficient for production at required rates and schedule.
Materials (Raw Materials, Components, Sub-assemblies and Sub-systems) | Maturity |  | Material maturity assessed. | Potential materials assessed for basic manufacturability. | Survey completed to determine if materials have been used before in a manufacturing environment. Preliminary plans in place to address producibility risks of new material. | Materials have been manufactured or produced in a prototype environment. Maturity efforts in place to address new material production risks for technology demonstration. | Material maturity verified through technology demonstration articles. Preliminary material specifications in place. | Materials maturity sufficient for pilot line build. Material specifications approved. | Materials proven and validated on System Demonstration and Development (SDD) production as adequate to support LRIP. Material specification stable. | Material is proven and controlled to specification in LRIP. | Material is proven and controlled to specification in FRP.
| Availability | Material availability assessed. | Material shortfalls identified. | New material scale-up issues assessed. | All exotic (difficult to obtain, process, or hazardous) materials identified. Lead times have been identified for all materials. | Availability issues addressed for prototype build. Significant material risks identified for all materials. Planning begun to address scale-up issues. | Availability issues addressed to meet technology demonstration articles. SDD long lead time items identified. Obsolescence issues identified. | Availability issues addressed to meet SDD builds. Long Lead procurement identified/planned for Low Rate Initial Production. Obsolescence plan in place. | Long Lead procurement initiated for LRIP. Availability issues pose no significant risk for LRIP. | Long Lead procurement initiated for Full Rate Production (FRP). Availability issues pose no significant risk for FRP. | Program is in FRP with no material availability issues.
| Supply Chain Management |  |  | Quick look at potential supply chain capability. | Survey completed for potential supply chain sources. | Supply chain sources identified. Sole/single/foreign source vendors have been identified and planning has begun to minimize risks. | Supply chain plans in place (e.g., teaming agreements, etc.) leading to an SDD contract award. | Effective supply chain management process in place. Completed assessment of supply chain first tier. | Supply chain stable and adequate to support LRIP. Completed assessment of supply chain second tier. | Supply chain is stable and adequate to support FRP. Long term agreements in place where practical. | Supply chain proven and supporting FRP requirements.
| Special Handling (i.e. shelf life, security, hazardous materials, storage environment, etc.) |  | Initial evaluation of potential EPA requirements completed. | Potential special handling concerns identified. Materials Safety Data Sheets (MSDS) prepared as necessary. | Special handling requirements identified. MSDS reviewed and updated. | Special handling requirement gaps identified. New special handling processes demonstrated in lab environment. | Plans to address special handling requirement gaps complete. | Special handling procedures developed. | Special handling procedures demonstrated on SDD or Technology insertion Programs production. Special handling issues pose no significant risk for LRIP. | Special handling procedures demonstrated in LRIP. Special handling issues pose no significant risk for FRP. | Special handling procedures effectively implemented in FRP.
Process Capability & Control | Modeling & Simulation (Product & Process) |  |  | Identification of proposed manufacturing concepts or producibility needs based on laboratory studies. | Production Modeling & Simulation approaches for Process or Product are identified. | Initial simulation models (product or process) developed at the component level. | Initial simulation models developed at the technology, sub-system or system level. | Simulation models used to determine system constraints and identify improvement opportunities. | Simulation models verified by SDD Article build, results used to improve process and determine that LRIP requirements can be met. | Simulation model verified by LRIP build, assist in management of LRIP and determine that FRP requirements can be met. | Simulation model verified by FRP build. Production simulation models used as tool to assist in management FRP.
| Manufacturing Process Maturity |  |  | Define Mfg State of the Art | Complete a survey to determine the current state of proposed processes. | Maturity has been assessed on similar processes in production. Process capability requirements have been identified. | Manufacturing processes demonstrated in production relevant environment. | Manufacturing processes demonstrated in a production representative environment. | Manufacturing processes verified for LRIP on a pilot line. Process capability data being collected or estimated. | Manufacturing processes & procedures are established and controlled in production to 3-sigma or other appropriate quality level. | Manufacturing processes & procedures are established and controlled in production to 6-sigma or other appropriate quality level.
| Process Yields and Rates |  |  |  | Yield and Rates assessment on proposed processes complete. | Target Yield and Rates established for production. Yield and Rate issues identified. Improvement plans initiated. | Yields and Rates evaluated in production relevant environment. Improvement plans on-going and updated. | Yields and Rates estimated in production representative environment. | Yields and Rates required to begin LRIP verified using SDD articles. | Yield and Rates targets achieved. Yield improvements on-going. | Yield and Rates targets achieved. Yield improvements on-going.
Quality Management | Quality Management including Supplier Quality. |  |  |  | Quality strategy identified as part of the Technology Development Strategy. | Quality Strategy refined in the System Engineering Plan and Key Charactaristic are Identified during Technology Demonstrations. | Initial Quality Plan and Quality Management System is in place. Quality Risks and Metrics have been identified. | Quality targets established. Demonstrate ability to collect and analyse quality data (process and system) in the production representative environment. | Quality targets demonstrated on pilot line. | Quality targets verified on production line. Continuous Quality Improvement begins. | Quality targets verified on production line. Continuous Quality Improvement on-going.
Mfg Personnel |  |  |  | Initial mfg skills identified. | Mfg skill sets identified to overcome production barriers | Skill sets identified to meet prototype production runs. Special skills certification and training requirements quantified | Mfg workforce skills available for production in a relevant environment. Training resources identified for production workforce. | Mfg workforce resource requirements identified for Pilot Line. Training resources identified for special skills deficiencies and LEAN Six Sigma Training | Mfg workforce resource requirements identified for LRIP. Ability of mfg workforce to produce repeatable products and workforce quality measured; training initiated for certification on special skills | LRIP personnel requirements met. FRP personnel requirements identified.. | FRP personnel requirements met. Production workforce skill sets maintained due to attrition of workforce.
Facilities |  |  |  | General industrial base (IB) capability identified for key technologies. | Specialized facility requirements/needs identified. | IB capabilities and gaps to support SDD and LRIP identified. Plan in place to fill gaps. | Mfg facility and facility development plans adequate to support SDD or Technology insertion Programs. | Facility capabilities for LRIP and FRP identified. Plan in place to fill gaps. Plant layout and design initiated. | Mfg facilities exist and are adequate to begin LRIP. Plans in place to support transition to FRP. | Mfg facilities in place and demonstrated in LRIP. and capacity plans adequate to support FRP decision. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Executable facilities surge plan available.
Mfg Management | Mfg Planning & Scheduling |  |  |  | Mfg strategy developed and integrated with acq strategy. Mfg risk mitigation efforts started. | Mfg strategy refined. Mfg risk mitigation efforts ongoing. | Initial mfg approach developed. All system design related mfg events included in Integrated Master Plan/Schedule. Mfg risk mitigation approach for SDD or Technology insertion Programs defined. | Initial Mfg Plan developed. Mfg risks integrated into Risk Mitigation Plan. | Mfg Plan Completed. All key manufacturing risks have been validated & mitigated using SDD or Technology Insertion Program work products. | Mfg Plan updated and validated for FRP. All manufacturing risks have been validated and mitigated using LRIP articles. | All manufacturing risks have been validated and mitigated using FRP articles.
| Materials Planning |  |  |  | Parts list in development with associated lead time calculations. | Parts list maturing, make/buy evaluations ongoing; lead times, quality, cost and other risks identified. | Most material decisions made (make/buy), material risk identified and plans made to mitigate. BOM initiated. | Analyses for Make/Buy decisions & BOM complete. Material planning systems in place for Pilot Line build. | Make/Buy decisions & BOM complete to support LRIP. Material planning systems validated on Pilot Line build. | Make/Buy decisions & BOM complete to support FRP. Material planning systems validated on LRIP build. | Program is in FRP with only process improvement/obsolescence make/buy or BOM changes allowed. Material Planning Systems validated on FRP build.
| Tooling / Special Test Equipment |  |  |  | Special Tooling / Special Test Equipment (STE) requirements are considered. | Identify Special Tooling /STE reqts & provide supporting rationale and schedule. | Prototype tooling concepts demonstrated in relevant mfg environment. | Production tooling and STE design and development efforts initiated. | All Tooling & Test Equipment proven on pilot line. Multiple tooling reqts identified for LRIP. | All Tooling & Test Equipment proven on LRIP. Multiple tooling reqts identified for FRP. | Proven Tooling & Test Equipment in place to support maximum FRP.

## Third
Version 6.4 | 2008-05-10
DoD Manufacturing Readiness Levels (MRLs)
Funding Type |  | 6.1 Basic Research | 6.2 Applied Research | 6.2 / 6.3 | 6.3 / 6.4 | 6.3 / 6.4 / 7.8 | 6.4 / 6.8 / 7.8 | 7.8 | 7.8 | 7.8 | 7.8 Title III
Acq Phase |  | Pre CR | Pre CR | Pre CR | CR - MS A | TD | MS B | SDD | MS C | LRIP - FRP | FRP
Thread | Sub-Thread | MRL 1 | MRL 2 | MRL 3 | MRL 4 | MRL 5 | MRL 6 | MRL 7 | MRL 8 | MRL 9 | MRL 10
Process Capability & Control | Modeling & Simulation (Product & Process) | Initial models developed. |  | Identification of proposed manufacturing concepts or producibility needs based on laboratory studies. | Production Modeling & Simulation approaches for Process or Product are identified. | Initial simulation models (product or process) developed at the component level. | Initial simulation models developed at the technology, sub-system or system level. | Simulation models used to determine system constraints and identify improvement opportunities. | Simulation models verified by SDD Article build, results used to improve process and determine that LRIP requirements can be met. | Simulation model verified by LRIP build, assist in management of LRIP and determine that FRP requirements can be met. | Simulation model verified by FRP build. Production simulation models used as tool to assist in management FRP.
| Manufacturing Process Maturity |  | Manufacturing State of the Art assessed. | Begin a survey to determine the current state of proposed processes. | Complete a survey to determine the current state of proposed processes. | Maturity has been assessed on similar processes in production. Process capability requirements have been identified. | Manufacturing processes demonstrated in production relevant environment. | Manufacturing processes demonstrated in a production representative environment. | Manufacturing processes verified for LRIP on a pilot line. Process capability data being collected or estimated. | Manufacturing processes & procedures are established and controlled in production to 3-sigma or other appropriate quality level. | Manufacturing processes & procedures are established and controlled in production to 6-sigma or other appropriate quality level.
| Process Yields and Rates |  |  |  | Yield and Rates assessment on proposed processes complete. | Target Yield and Rates established for production. Yield and Rate issues identified. Improvement plans initiated. | Yields and Rates evaluated in production relevant environment. Improvement plans on-going and updated. | Yields and Rates estimated in production representative environment. | Yields and Rates required to begin LRIP verified using SDD articles. | Yield and Rates targets achieved. Yield improvements on-going. | Yield and Rates targets achieved. Yield improvements on-going.
Quality Management | Quality Management including Supplier Quality. |  |  |  | Quality strategy identified as part of the Technology Development Strategy. | Quality Strategy refined in the System Engineering Plan and Key Charactaristic are Identified during Technology Demonstrations. | Initial Quality Plan and Quality Management System is in place. Quality Risks and Metrics have been identified. | Quality targets established. Demonstrate ability to collect and analyse quality data (process and system) in the production representative environment. | Quality targets demonstrated on pilot line. | Quality targets verified on production line. Continuous Quality Improvement begins. | Quality targets verified on production line. Continuous Quality Improvement on-going.
Mfg Personnel |  |  |  | Initial mfg skills identified. | Mfg skill sets identified to overcome production barriers | Skill sets identified to meet prototype production runs. Special skills certification and training requirements quantified | Mfg workforce skills available for production in a relevant environment. Training resources identified for production workforce. | Mfg workforce resource requirements identified for Pilot Line. Training resources identified for special skills deficiencies and LEAN Six Sigma Training | Mfg workforce resource requirements identified for LRIP. Ability of mfg workforce to produce repeatable products and workforce quality measured; training initiated for certification on special skills | LRIP personnel requirements met. FRP personnel requirements identified.. | FRP personnel requirements met. Production workforce skill sets maintained due to attrition of workforce.
Facilities |  |  |  | General industrial base (IB) capability identified for key technologies. | Specialized facility requirements/needs identified. | IB capabilities and gaps to support SDD and LRIP identified. Plan in place to fill gaps. | Mfg facility and facility development plans adequate to support SDD or Technology insertion Programs. | Facility capabilities for LRIP and FRP identified. Plan in place to fill gaps. Plant layout and design initiated. | Mfg facilities exist and are adequate to begin LRIP. Plans in place to support transition to FRP. | Mfg facilities in place and demonstrated in LRIP. and capacity plans adequate to support FRP decision. | Production facilities in place and capacity demonstrated to meet maximum FRP requirements. Executable facilities surge plan available.
Mfg Management | Mfg Planning & Scheduling |  |  |  | Mfg strategy developed and integrated with acq strategy. Mfg risk mitigation efforts started. | Mfg strategy refined. Mfg risk mitigation efforts ongoing. | Initial mfg approach developed. All system design related mfg events included in Integrated Master Plan/Schedule. Mfg risk mitigation approach for SDD or Technology insertion Programs defined. | Initial Mfg Plan developed. Mfg risks integrated into Risk Mitigation Plan. | Mfg Plan Completed. All key manufacturing risks have been validated & mitigated using SDD or Technology Insertion Program work products. | Mfg Plan updated and validated for FRP. All manufacturing risks have been validated and mitigated using LRIP articles. | All manufacturing risks have been validated and mitigated using FRP articles.
| Materials Planning |  |  |  | Parts list in development with associated lead time calculations. | Parts list maturing, make/buy evaluations ongoing; lead times, quality, cost and other risks identified. | Most material decisions made (make/buy), material risk identified and plans made to mitigate. BOM initiated. | Analyses for Make/Buy decisions & BOM complete. Material planning systems in place for Pilot Line build. | Make/Buy decisions & BOM complete to support LRIP. Material planning systems validated on Pilot Line build. | Make/Buy decisions & BOM complete to support FRP. Material planning systems validated on LRIP build. | Program is in FRP with only process improvement/obsolescence make/buy or BOM changes allowed. Material Planning Systems validated on FRP build.
| Tooling / Special Test Equipment |  |  |  | Special Tooling / Special Test Equipment (STE) requirements are considered. | Identify Special Tooling /STE reqts & provide supporting rationale and schedule. | Prototype tooling concepts demonstrated in relevant mfg environment. | Production tooling and STE design and development efforts initiated. | All Tooling & Test Equipment proven on pilot line. Multiple tooling reqts identified for LRIP. | All Tooling & Test Equipment proven on LRIP. Multiple tooling reqts identified for FRP. | Proven Tooling & Test Equipment in place to support maximum FRP.